## Estimate - Project Tasks
Project Estimate Description
Company | Ebix
Project | Motor Claims Admin System - ComfortDelGro Insurance Brokers Pte Ltd (CDG)
Project Release | Release 1
Development Sprint | Requirements without Sprint,
Priority | Requirements without Priority,
Reference Number | Requirement Short Description | Development Sprint | Priority | Requirement Category | Deliverable Type | Requires Research Time | Requirement Long Description | Expected Pessimistic Estimate in Hours | Expected Most Likely Estimate in Hours | Expected Optimistic Estimate in Hours | Expected Pessimistic Estimate in Workdays | Expected Optimistic Estimate in Workdays | Final Estimation (Hours)
1 | To design a 3-tier architecture. This will include Business Tier, Data Access Tier and Presentation Tier layers. |  | High |  | Functional | No |  | 20 | 14 | 12 | 3 | 2 | 14.6667
2 | Migration of existing Claim module including Claim Admin section of Beazley to .Net Framework 4.0. |  | High |  | Functional | Yes |  | 120 | 100 | 90 | 15 | 11 | 101.6667
3 | e-filing system to be migrated in .Net framework 4.0. |  | High |  | Functional | Yes | More details required about e-filing project. | 60 | 55 | 50 | 8 | 6 | 55
4 | Diary Setup - Workflow - Claim Admin System |  | High |  | Functional | No |  | 40 | 37 | 30 | 5 | 4 | 36.3333
5 | Worklist set up - This will include landing page displaying the worklist for the user as in EAW. |  | High |  | Functional |  |  | 70 | 65 | 60 | 9 | 8 | 65
6 | Users to view and track all e-filed accident cases. A System Administration function to set access rights for Users and User Groups |  | High |  | Functional | Yes |  | 50 | 35 | 20 | 6 | 3 | 35
7 | Third Party - New tab - Sample screen layout to be taken from EAW |  | High |  | Functional |  |  | 35 | 30 | 25 | 4 | 3 | 30
8 | Occurrence Details - New tab - Sample screen layout to be taken from EAW |  | High |  | Functional |  |  | 35 | 30 | 25 | 4 | 3 | 30
9 | Attachments - New tab - Sample screen layout to be taken from EAW |  | High |  | Functional |  |  | 35 | 30 | 25 | 4 | 3 | 30
10 | Reserve Summary- All Claimants - New tab |  | High |  | Functional |  |  | 40 | 35 | 30 | 5 | 4 | 35
11 | System Admin section |  | High |  | Functional |  |  | 20 | 18 | 15 | 3 | 2 | 17.8333
12 | UI – using bootstrap for browser independence and HTML5 Complaint |  | High |  | Functional |  |  | 120 | 100 | 95 | 15 | 12 | 102.5
13 | Database will be multi-language |  | High |  | Functional |  |  | 20 | 16 | 10 | 3 | 1 | 15.6667
14 | Based on agreed formats and letter types, the system will generate standard formatted letters (For one letter and one page.) |  | High |  | Functional |  |  | 30 | 27 | 25 | 4 | 3 | 27.1667
15 | Archival functions to improve system performance (Limited to 5 tables) |  | High |  | Functional | Yes |  | 30 | 23 | 20 | 4 | 3 | 23.6667
16 | Archival functions to improve system performance (Attachments / Images build up over the years) |  | High |  | Functional | Yes |  | 40 | 30 | 35 | 5 | 4 | 32.5
17 | Penetration & Security testing |  | High |  | Functional | Yes |  | 50 | 35 | 23 | 6 | 3 | 35.5
18 | A file upload function will be considered to handle claims data files that will be provided by insurers. |  | High |  | Functional |  |  | 12 | 11 | 8 | 2 | 1 | 10.6667
Total | [7 empty] | 827 | 691 | 598 | 105 | 76 | 698.1667