## Estimate - Project Tasks
Project Estimate Description
Company | Ebix
Project | Motor Claims Admin System - ComfortDelGro Insurance Brokers Pte Ltd (CDG)
Project Release | Release 1
Development Sprint | Requirements without Sprint,
Priority | Requirements without Priority,
Reference Number | Requirement Short Description | Development Sprint | Priority | Requirement Category | Deliverable Type | Requires Research Time | Requirement Long Description | Expected Pessimistic Estimate in Hours | Expected Optimistic Estimate in Hours | Expected Pessimistic Estimate in Workdays | Expected Optimistic Estimate in Workdays
1 | To design a 3-tier architecture. This will include Business Tier, Data Access Tier and Presentation Tier layers. |  | High |  | Functional | No |  | 20 | 12 | 3 | 2
2 | Migration of existing Claim module including Claim Admin section of Beazley to .Net Framework 4.0. |  | High |  | Functional | Yes |  | 120 | 90 | 15 | 11
3 | e-filing system to be migrated in .Net framework 4.0. |  | High |  | Functional | Yes | More details required about e-filing project. | 60 | 50 | 8 | 6
4 | Diary Setup - Workflow - Claim Admin System |  | High |  | Functional | No |  | 30 | 40 | 4 | 5
5 | Worklist set up - This will include landing page displaying the worklist for the user as in EAW. |  | High |  | Functional |  |  | 70 | 60 | 9 | 8
6 | Users to view and track all e-filed accident cases. A System Administration function to set access rights for Users and User Groups |  | High |  | Functional | Yes |  | 50 | 20 | 6 | 3
7 | Third Party - New tab - Sample screen layout to be taken from EAW |  | High |  | Functional |  |  | 35 | 25 | 4 | 3
8 | Occurrence Details - New tab - Sample screen layout to be taken from EAW |  | High |  | Functional |  |  | 35 | 25 | 4 | 3
9 | Attachments - New tab - Sample screen layout to be taken from EAW |  | High |  | Functional |  |  | 35 | 25 | 4 | 3
10 | Reserve Summary- All Claimants - New tab |  | High |  | Functional |  |  | 40 | 30 | 5 | 4
11 | System Admin section |  | High |  | Functional |  |  | 10 | 10 | 1 | 1
12 | UI – using bootstrap for browser independence and HTML5 Complaint |  | High |  | Functional |  |  | 120 | 95 | 15 | 12
13 | Database will be multi-language |  | High |  | Functional |  |  | 10 | 10 | 1 | 1
14 |  Based on agreed formats and letter types, the system will generate standard formatted letters |  | High |  | Functional |  |  | 25 | 25 | 3 | 3
15 |  Archival functions to improve system performance |  | High |  | Functional | Yes |  | 90 | 80 | 11 | 10
16 | Penetration & Security testing |  | High |  | Functional | Yes |  | 50 | 20 | 6 | 3
16 |  A file upload function will be considered to handle claims data files that will be provided insurers. |  | High |  | Functional |  |  | 10 | 10 | 1 | 1
Total | [7 empty] | 810 | 627 | 100 | 79
Note on B13: praveen.kasana: Migration will involve 40 to 45 files.
Note on B14: praveen.kasana: Please provide us more details on this one. We would be updating estimate when we have more details from Aasai. As of now, Have put in the approximate estimate.
Note on B15: praveen.kasana: This section will be similar to what we have in EAW.
Note on B22: praveen.kasana: We have to add new master controls table. For Example : - Vehicle Make and Model  Authority Limits Master
Note on B25: praveen.kasana: Estimate provided is as per one standard letter.
Note on B26: praveen.kasana: Mr.Yip, Do we have this funtionality in place in Beazley ?. Please confrim.If NO, we might have to increase the estimation time. Right now I am putting the pessimistic estimation. Reply from Mr. Yip : - There is no archival function in Beazley version, so this will be a new function. The function is to address system performance, which could be dragged down by attachments and images build up over the years.
Note on B27: praveen.kasana: Please provide more details ont his one. This could cover following : Restrict XSS attacks. Restrict SQL injection and Form Injection. We will be using EAW Encryption methods if required.
Note on B28: praveen.kasana: This will be handled in Attachment. Please confirm if this section will be different from Attachment tab.