## 10 april 2015
Modules | % | India Ebix Remarks
Development & QA- System Admin | 85
Development & QA - Upload | 85
Development & QA - Claim (Bus & Train only) | 70 | * % complete decreased because new functionality has been raised on iTrack 19.
Development & QA- Claim Enquiry | 80
Development & QA - Document Generation | 30
Development & QA - Document Print | 30
Development & QA - Unreported Claim | 10 | * Similar to claim ( bus & Tracn only ), Please remove it from this list and as well from project plan.
Development & QA - Security Management System | 90 | * Please go thorough security management system and provide us feedback , if it require any changes.
Development & QA - LOG Request | 85

## 3 april 2015
Modules | % | Remarks 3 april 2015
Development & QA- System Admin | 80 | 1) During last month we got following requirements and will Release in march. * Common master creation for miscellaneous listing - iTrack# 2 * Permission list change based on dashboard layout - iTrack# 14 * Roles and assignment drop down list add - iTrack# 5 * Arrangement of system admin menus - iTrack# 4 * Vehicle upload and bus captain listing upload - iTrack #7 * Removal of country access for user tab screen - iTrack #8 * USer Menu Section - Queries - iTrack #21 * FAL Master Creation and change in user tab - iTrack #23 * Short country Code - iTrack #27
Development & QA - Upload | 80 | * Test cases has been issues, we will release updated Test cases, please proceed testing after you got updated test case file for upload.
Development & QA - Claim (Bus & Train only) | 80 | 1) During last month we got following requirements and will Release in march. * Deductible Alert Indicator - iTrack# 22 *New Claim Registration for Unreported Claims - iTrack# 1 * Claim flow specification - iTrack# 11 Please test and provide us feedback.
Development & QA- Claim Enquiry | 50 | 1) During last month we got following requirements and will Release in march. * Claim flow specification - iTrack# 11
Development & QA - Document Generation | 30 | * As per given remarks by dexter , phase is on hold * Please refer - iTrack# 10
Development & QA - Document Print | 30 | * As per given remarks by dexter , phase is on hold * Please refer - iTrack# 10
Development & QA - Unreported Claim | 10 | * Similar to "Development & QA - Claim (Bus & Train only)" as manual creation of claim is considered as unreported claim
Development & QA - Security Management System | 90 | 1) During last month we got following requirements and will Release in march. * Permission list change based on dashboard layout - iTrack# 14
Development & QA - LOG Request | 70