## V1.0
| Duration | Work | Start | Finish | Predecessors | Resource Names | Actual Duration
MCAS
1 Project Initiation
1.1 Project Scope Definition | [5 empty] | Singapore
1.2 Project Plan Development | [5 empty] | Singapore
1.3 Project Scope Completed | [5 empty] | Singapore
2 Requirement Gathering
2.1 Dashboard Requirements
2.2 Diary Listing Requirements
2.2.1 Diary Items
2.2.2 Assigned Tasks
2.2.3 Escalation Tasks
2.3 System Admin Requirements
2.3.1 Upload Main Menu
2.3.2 User Admin
2.3.3 Service Provider Master
2.4 Claim Requirements
2.4.1 Buses
2.4.2 Trains
2.4.3 Taxis
2.4.4 Rental Cars
2.4.5 Private Cars
2.5 Upload Requirements
2.5.1 TAC Upload
2.5.2 Claim File Upload
2.6 Claim Enquiry Requirements
2.6.1 Claims
2.6.2 Claim Documents Printing
2.6.3 Job Schedule Enquiry
2.7 Security Management System
2.8 Document Print
2.8.1 Claim Payment Document Printing
2.8.2 Claim Registration Document Printing
2.9 Document Generation Module
2.10 Requirements signed off by client
3 Requirements Finalized in TFS
3.1 Document Upload in TFS
4 Design UI and Functionality
4.1 Bus UI and Functionality
4.2 Train UI and Functionality
4.3 Taxi UI and Functionality
4.4 Rental Cars UI and Functionality
4.5 Private Cars UI and Functionality
4.6 Bus UI and Functionality signed off by client
4.7 Train UI and Functionality signed off by client
4.8 Taxi UI and Functionality signed off by client
4.9 Rental Cars UI and Functionality signed off by client
4.10 Private Cars UI and Functionality signed off by client
5 Iterative Development and Testing
5.1 Dashboard
5.1.1 User Manual
5.1.2 Test Approach/Test Cases
5.1.3 QA Testing
5.1.4 UAT
5.2 Diary Listing
5.2.1 Diary Items
5.2.2 Assigned Tasks
5.2.3 Escalation Tasks
5.2.4 User Manual
5.2.5 Test Approach/Test Cases
5.2.6 QA Testing
5.2.7 UAT
5.3 System Admin
5.3.1 Upload Main Menu
5.3.2 User Admin
5.3.3 Service Provider Master
5.3.4 User Manual
5.3.5 Test Approach/Test Cases
5.3.6 QA Testing
5.3.7 UAT
5.4 Claim
5.4.1 Buses
5.4.2 Trains
5.4.3 Taxis
5.4.4 Rental Cars
5.4.5 Private Cars
5.4.6 User Manual
5.4.7 Test Approach/Test Cases
5.4.8 QA Testing
5.4.9 UAT
5.5 Upload
5.5.1 TAC Upload
5.5.2 Claim File Upload
5.5.3 User Manual
5.5.4 Test Approach/Test Cases
5.5.5 QA Testing
5.5.6 UAT
5.6 Claim Enquiry
5.6.1 Claims
5.6.2 Claim Documents Printing
5.6.3 Job Schedule Enquiry
5.6.4 User Manual
5.6.5 Test Approach/Test Cases
5.6.6 QA Testing
5.6.7 UAT
5.7 Security Management System
5.7.1 User Manual
5.7.2 Test Approach/Test Cases
5.7.3 QA Testing
5.7.4 UAT
5.8 Document Print
5.8.1 Claim Payment Document Printing
5.8.2 Claim Registration Document Printing
5.8.3 User Manual
5.8.4 Test Approach/Test Cases
5.8.5 QA Testing
5.8.6 UAT
5.9 Document Generation Module
5.9.1 User Manual
5.9.2 Test Approach/Test Cases
5.9.3 QA Testing
5.9.4 UAT
6 QA Test Scripts
6.1 Testing Approach Development/Confirmation
6.2 Test Condition Development
6.3 Test Script Development
6.4 Expected Results Development
7 QA Testing
7.1 QA Testing
7.2 Review results
8 End-to-end UAT
8.1 Access to UAT Environment
8.2 Product Testing
9 Client UAT
9.1 Access to UAT Environment
9.2 Product Testing
10 Deployment
10.1 Deployment Approach
10.2 Platform Readiness
10.3 Software Installation
10.4 UAT Sign-off
10.5 Go Live Preparation
10.6 Support Kick Off