## Sheet1
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Work Complete | India Ebix Remarks | Items Pending at CDGI
Manually Scheduled | MCAS Project | 506 days | Wed 1/1/14 | Wed 9/12/15 |  |  | 67%
Manually Scheduled | 1 Project Initiation | 262 days | Wed 1/1/14 | Thu 1/1/15 |  | Singapore | 100%
Manually Scheduled | 2 Requirement Gathering | 122 days | Thu 1/1/15 | Fri 19/6/15 |  | Singapore | 73%
Manually Scheduled | 2.1 System Admin Requirements | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 90%
Manually Scheduled | 2.1.1 Upload Main Menu | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 21%
Manually Scheduled | 2.1.1.1 Vehicle Listing Upload | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 21%
Manually Scheduled | 2.1.1.2 Bus Captain Listing | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 21% | Waiting for sample upload file
Manually Scheduled | 2.1.2 User Admin | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.2.1 Entity Details | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.2.2. User Groups | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.2.3 User | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.2.4 Department Master | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.2.5 Password Setup | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.2.6 Release Locked Users | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.2.7 Country for User Access | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.3 Service Provider | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.4 Nature Of Loss | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.5 Type of Loss | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.6 Main Class Business | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.7 Sub Class | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.8 Claims Expense Master | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.9 Claims Close Reason Master | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.10 Currency Master | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.11 Exchange Rate Master | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.12 Vehicle Class | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.13 Vehicle Make | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.14 Vehicle Model | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.15 Insurance Policy | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.16 GST Setting | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.17 Organization | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.18 Claim Officer Duty | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.19 LOU Rate | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.1.20 Interchange | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.1.21 Deductible | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.2 Upload Requirements | 17 days | Thu 29/1/15 | Fri 20/2/15 |  | Singapore | 47%
Manually Scheduled | 2.2.1 TAC Upload | 17 days | Thu 29/1/15 | Fri 20/2/15 |  | Singapore | 100%
Manually Scheduled | 2.2.2 Claim File Upload | 17 days | Thu 29/1/15 | Fri 20/2/15 |  | Singapore | 100%
Manually Scheduled | 2.2.3 SAP File Upload | 22 days | Mon 1/6/15 | Tue 30/6/15 |  | Singapore | 0% | Phase 2 delivery | Phase 2 delivery
Manually Scheduled | 2.3 Claim Requirements | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 78%
Manually Scheduled | 2.3.1 Buses | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.1 Accident | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.2 Claim | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.3 Service Provider | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.4 Notes | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.5 Tasks | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.6 Attachment | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.7 Dairy | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.8 Reassigned Dairy | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.9 Reserve | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.10 Reserve History | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.11 Mandate | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.12 Mandate History | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.13 Payment | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.14 Payment History | 22 days | Thu 1/1/15 | Fri 30/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.15 Recovery | 32 days | Thu 1/1/15 | Fri 13/2/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.16 Transaction History | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.1.17 Alert Indicator for Deductible | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Manually Scheduled | 2.3.2 Trains | 22 days | Mon 16/2/15 | Tue 17/3/15 |  | Singapore | 0%
Manually Scheduled | 2.3.3 Taxis | 22 days | Tue 17/3/15 | Wed 15/4/15 |  | Singapore | 0%
Manually Scheduled | 2.3.4 Rental Cars | 22 days | Wed 15/4/15 | Thu 14/5/15 |  | Singapore | 0%
Manually Scheduled | 2.3.5 Private Cars | 22 days | Thu 14/5/15 | Fri 12/6/15 |  | Singapore | 0%
Manually Scheduled | 2.4 Dashboard Requirements | 37 days | Thu 1/1/15 | Fri 20/2/15 |  | Singapore | 80% | UI of permission start development | Pending clarification from CDGI
Manually Scheduled | 2.5 Diary Listing | 37 days | Thu 1/1/15 | Fri 20/2/15 |  | Singapore | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 2.5.1 Diary Items | 37 days | Thu 1/1/15 | Fri 20/2/15 |  | Singapore | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 2.5.2 Assigned Tasks | 37 days | Thu 1/1/15 | Fri 20/2/15 |  | Singapore | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 2.5.3 Escalation Tasks | 37 days | Thu 1/1/15 | Fri 20/2/15 |  | Singapore | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 2.6 Claim Enquiry Requirements | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 100%
Manually Scheduled | 2.6.1 Claims | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 100%
Manually Scheduled | 2.6.2 Claim Documents Printing | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 100%
Manually Scheduled | 2.6.3 Job Schedule Enquiry | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 100%
Manually Scheduled | 2.7 Document Generation Module | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 0% | pending for requirement detail | Pending clarification from CDGI
Manually Scheduled | 2.8 Document Print | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 0% |  | Pending clarification from CDGI
Manually Scheduled | 2.9 Unreported Claim | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 100%
Manually Scheduled | 2.10 Security Management System | 27 days | Thu 29/1/15 | Fri 6/3/15 |  | Singapore | 0%
Manually Scheduled | 2.11 Requirements signed off by client | 5 days | Mon 15/6/15 | Fri 19/6/15 |  | Singapore | 29%
Auto Scheduled | 2.12 New Requirement - New Master Tables | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Manually Scheduled | 2.12.1 iTrack #2 | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Auto Scheduled | 2.13 New Requirement - LOG Request | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Manually Scheduled | 2.13.1 iTrack #10 | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Auto Scheduled | 2.14 New Requirement - FAL Masters | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Manually Scheduled | 2.14.1 iTrack #23 | 1 day? | Thu 1/1/15 | Thu 1/1/15 |  | Singapore | 100%
Auto Scheduled | 3 Requirements Finalized in TFS | 392 days | Mon 3/3/14 | Tue 1/9/15 |  | India | 57%
Manually Scheduled | 4 Design UI and Functionality | 299 days | Thu 1/5/14 | Tue 23/6/15 |  | India | 73%
Manually Scheduled | 4.1 System Admin Requirements | 307 days | Thu 1/5/14 | Fri 3/7/15 |  | India | 81% |  | Pending clarification from CDGI
Manually Scheduled | 4.1.1 Upload Main Menu | 192 days | Sun 1/6/14 | Mon 23/2/15 |  | India | 80%
Auto Scheduled | 4.1.1.1 Vehicle Listing Upload | 20 days | Mon 5/5/14 | Wed 2/7/14 |  | Singapore | 100%
Manually Scheduled | 4.1.1.2 Bus Captain Listing | 10 days | Tue 10/2/15 | Mon 23/2/15 | 10 | Singapore | 0% | Waiting to get upload sample filel
Auto Scheduled | 4.1.2 User Admin | 217 days | Thu 1/5/14 | Fri 27/2/15 | 11 | India | 88%
Manually Scheduled | 4.1.2.1 Entity Details | 15 days | Thu 1/5/14 | Wed 21/5/14 | 12 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 4.1.2.2. User Groups | 20 days | Mon 2/2/15 | Fri 27/2/15 | 13 | India | 100%
Manually Scheduled | 4.1.2.3 User | 20 days | Fri 30/1/15 | Thu 26/2/15 | 14 | India | 100%
Manually Scheduled | 4.1.2.4 Department Master | 10 days | Fri 30/1/15 | Thu 12/2/15 | 15 | India | 100%
Manually Scheduled | 4.1.2.5 Password Setup | 5 days | Fri 30/1/15 | Thu 5/2/15 | 16 | India | 100%
Manually Scheduled | 4.1.2.6 Release Locked Users | 5 days | Fri 30/1/15 | Thu 5/2/15 | 17 | India | 100%
Manually Scheduled | 4.1.2.7 Country for User Access | 10 days | Fri 30/1/15 | Thu 12/2/15 | 18 | India | 100% | Requirement revoked and menu removed from Application
Auto Scheduled | 4.1.3 Service Provider | 10 days | Wed 5/11/14 | Tue 18/11/14 |  | India | 100%
Manually Scheduled | 4.1.3.1 Insurer Master | 10 days | Wed 5/11/14 | Tue 18/11/14 |  | India | 100%
Manually Scheduled | 4.1.3.2 Surveyor Master | 10 days | Wed 5/11/14 | Tue 18/11/14 |  | India | 100%
Manually Scheduled | 4.1.3.3 Lawyer Master | 10 days | Wed 5/11/14 | Tue 18/11/14 |  | India | 100%
Manually Scheduled | 4.1.3.4 Workshop/Dept Master | 10 days | Wed 5/11/14 | Tue 18/11/14 |  | India | 100%
Manually Scheduled | 4.1.3.5 Hospital Master | 10 days | Wed 5/11/14 | Tue 18/11/14 |  | India | 100%
Manually Scheduled | 4.1.3.6 Adjuster Master | 10 days | Wed 5/11/14 | Tue 18/11/14 |  | India | 100%
Manually Scheduled | 4.1.4 Nature Of Loss | 15 days | Wed 4/6/14 | Tue 24/6/14 |  | India | 100%
Manually Scheduled | 4.1.5 Type of Loss | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100% | Waiting for functionality
Manually Scheduled | 4.1.6 Main Class Business | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100% | Waiting for functionality
Manually Scheduled | 4.1.7 Sub Class | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100% | Waiting for functionality
Manually Scheduled | 4.1.8 Claims Expense Master | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100% | Waiting for functionality
Manually Scheduled | 4.1.9 Claims Close Reason Master | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100% | Waiting for functionality
Manually Scheduled | 4.1.10 Currency Master | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100%
Manually Scheduled | 4.1.11 Exchange Rate Master | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100%
Manually Scheduled | 4.1.12 Vehicle Class | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100%
Manually Scheduled | 4.1.13 Vehicle Make | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100%
Manually Scheduled | 4.1.14 Vehicle Model | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100%
Manually Scheduled | 4.1.15 Insurance Policy | 15 days | Wed 4/6/14 | Tue 24/6/14 |  | India | 100%
Manually Scheduled | 4.1.16 GST Setting | 10 days | Wed 4/6/14 | Tue 17/6/14 |  | India | 100% | Waiting for functionality
Manually Scheduled | 4.1.17 Organization | 20 days | Mon 15/12/14 | Fri 9/1/15 |  | India | 100%
Manually Scheduled | 4.1.18 Claim Officer Duty | 10 days | Wed 3/9/14 | Tue 16/9/14 |  | India | 100% |  | Pending clarification from CDGI
Manually Scheduled | 4.1.19 LOU Rate | 10 days | Wed 10/9/14 | Tue 23/9/14 |  | India | 100%
Manually Scheduled | 4.1.20 Interchange | 10 days | Wed 10/9/14 | Tue 23/9/14 |  | India | 100%
Manually Scheduled | 4.1.21 Deductible | 10 days | Mon 15/12/14 | Fri 26/12/14 |  | India | 100%
Manually Scheduled | 4.2 Upload | 20 days | Thu 29/1/15 | Wed 25/2/15 |  | India | 50%
Manually Scheduled | 4.2.1 TAC Upload | 20 days | Thu 29/1/15 | Wed 25/2/15 |  | India | 100%
Manually Scheduled | 4.2.2 Claim File Upload | 20 days | Thu 29/1/15 | Wed 25/2/15 |  | India | 100%
Manually Scheduled | 4.2.3 SAP File Upload | 20 days | Thu 29/1/15 | Wed 25/2/15 |  | India | 0% | Phase 2 delivery | Phase 2 delivery
Auto Scheduled | 4.3 Claim | 156 days | Thu 2/10/14 | Thu 7/5/15 |  | India | 75%
Manually Scheduled | 4.3.1 Buses | 96 days | Thu 2/10/14 | Thu 12/2/15 |  | India | 90%
Manually Scheduled | 4.3.1.1 Accident | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.1.2 Claim | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.1.3 Service Provider | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.1.4 Notes | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.1.5 Tasks | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.1.6 Attachment | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.1.7 Dairy | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.1.8 Reassigned Dairy | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Auto Scheduled | 4.3.1.9 Reserve | 31 days | Fri 21/11/14 | Fri 2/1/15 |  | India | 100%
Manually Scheduled | 4.3.1.10 Reserve History | 31 days | Fri 21/11/14 | Fri 2/1/15 |  | India | 100%
Manually Scheduled | 4.3.1.11 Mandate | 31 days | Fri 21/11/14 | Fri 2/1/15 |  | India | 100%
Manually Scheduled | 4.3.1.12 Mandate History | 31 days | Fri 21/11/14 | Fri 2/1/15 |  | India | 100%
Manually Scheduled | 4.3.1.13 Payment | 31 days | Fri 5/12/14 | Fri 16/1/15 |  | India | 83%
Manually Scheduled | 4.3.1.14 Payment History | 31 days | Fri 5/12/14 | Fri 16/1/15 |  | India | 83%
Manually Scheduled | 4.3.1.15 Recovery | 31 days | Thu 1/1/15 | Thu 12/2/15 |  | India | 22% | Waiting for functionality
Manually Scheduled | 4.3.1.16 Transaction History | 20 days | Thu 2/10/14 | Wed 29/10/14 |  | India | 100%
Manually Scheduled | 4.3.1.17 Alert Indicator for Deductible |  |  |  |  | India | 0%
Manually Scheduled | 4.3.2 Trains | 31 days | Thu 2/10/14 | Thu 13/11/14 |  | India | 100%
Manually Scheduled | 4.3.3 Taxis | 20 days | Tue 10/3/15 | Mon 6/4/15 |  | India | 0% | Waiting for functionality
Manually Scheduled | 4.3.4 Rental Cars | 20 days | Fri 10/4/15 | Thu 7/5/15 |  | India | 0% | Waiting for functionality
Manually Scheduled | 4.3.5 Private Cars | 20 days | Fri 10/4/15 | Thu 7/5/15 |  | India | 0% | Waiting for functionality
Manually Scheduled | 4.4 Dashboard | 15 days | Tue 10/2/15 | Mon 2/3/15 |  | India | 80%
Manually Scheduled | 4.4.1 Sections of Dashboard as per User Group | 15 days | Tue 10/2/15 | Mon 2/3/15 |  | India | 80% | Waiting for functionality | Pending clarification from CDGI
Auto Scheduled | 4.5 Diary Listing | 10 days | Tue 10/2/15 | Mon 23/2/15 |  | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 4.5.1 Diary Items | 10 days | Tue 10/2/15 | Mon 23/2/15 |  | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 4.5.2 Assigned Tasks | 10 days | Tue 10/2/15 | Mon 23/2/15 |  | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 4.5.3 Escalation Tasks | 10 days | Tue 10/2/15 | Mon 23/2/15 |  | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 4.6 Claim Enquiry | 70 days | Thu 29/1/15 | Wed 6/5/15 |  | India | 100%
Manually Scheduled | 4.6.1 Claims | 30 days | Thu 29/1/15 | Wed 11/3/15 |  | India | 100%
Manually Scheduled | 4.6.2 Claim Documents Printing | 30 days | Fri 20/3/15 | Thu 30/4/15 |  | India | 100%
Manually Scheduled | 4.6.3 Job Schedule Enquiry | 10 days | Thu 29/1/15 | Wed 11/2/15 |  | India | 100%
Manually Scheduled | 4.7 Document Generation Module | 30 days | Mon 2/3/15 | Fri 10/4/15 |  | India | 0% | Waiting for functionality | Pending clarification from CDGI
Manually Scheduled | 4.7.1 Document Generation Criteria | 30 days | Mon 2/3/15 | Fri 10/4/15 |  | India | 0% | Waiting for functionality
Manually Scheduled | 4.8 Document Print | 30 days | Wed 25/3/15 | Tue 5/5/15 |  | India | 0% |  | Pending clarification from CDGI
Manually Scheduled | 4.8.1 Claim Payment Document Printing | 30 days | Wed 25/3/15 | Tue 5/5/15 |  | India | 0% | Waiting for functionality | waiting To Get Details
Manually Scheduled | 4.8.2 Claim Registration Document Printing | 30 days | Wed 25/3/15 | Tue 5/5/15 |  | India | 0% | Waiting for functionality
Manually Scheduled | 4.9 Unreported Claim | 10 days | Thu 5/2/15 | Wed 18/2/15 |  | India | 100% | Removed | Removed
Manually Scheduled | 4.10 Security Management System | 30 days | Mon 10/11/14 | Fri 19/12/14 |  | India | 100%
Manually Scheduled | 4.10.1 Permission Screen UI | 15 days | Mon 10/11/14 | Fri 28/11/14 |  | India | 100% |  | waiting To Get Details
Manually Scheduled | 4.10.2 Permission screen functionality | 15 days | Mon 10/11/14 | Fri 28/11/14 |  | India | 100% |  | waiting To Get Details
Manually Scheduled | 4.11 UI and Design signed off by client | 5 days | Tue 17/6/14 | Mon 23/6/14 |  | India | 100%
Auto Scheduled | 4.12 New Requirement - New Master Tables | 6 days | Tue 3/3/15 | Tue 10/3/15 |  | India | 100%
Manually Scheduled | 4.12.1 iTrack #2 | 6 days | Tue 3/3/15 | Tue 10/3/15 |  | India | 100%
Auto Scheduled | 4.13 New Requirement - LOG Request | 5 days | Sat 3/10/15 | Sat 10/10/15 |  | India | 100%
Manually Scheduled | 2.13.1 iTrack #10 | 7 days | Sat 3/10/15 | Sat 10/10/15 |  | India | 100%
Auto Scheduled | 4.14 New Requirement - FAL Masters | 5 days | Sat 3/10/15 | Sat 10/10/15 |  | India | 100%
Manually Scheduled | 2.14.1 iTrack #23 | 7 days | Sat 3/10/15 | Sat 10/10/15 |  | India | 100%
Manually Scheduled | 5 Iterative Development and Testing | 305 days | Thu 22/5/14 | Wed 22/7/15 | 96 | India | 52%
Manually Scheduled | 5.1 System Admin | 240 days | Tue 1/7/14 | Mon 1/6/15 |  | India | 80%
Auto Scheduled | 5.1.1 Upload Main Menu | 129 days | Tue 9/9/14 | Fri 6/3/15 | 100 | India | 33%
Manually Scheduled | 5.1.1.1 Vehicle Listing Upload | 10 days | Tue 9/9/14 | Mon 22/9/14 | 101 | India | 100%
Manually Scheduled | 5.1.1.2 Bus Captain Listing | 10 days | Mon 23/2/15 | Fri 6/3/15 | 102 | India | 0% | Waiting for functionality
Auto Scheduled | 5.1.2 User Admin | 212 days | Thu 22/5/14 | Fri 13/3/15 | 103 | India | 84%
Manually Scheduled | 5.1.2.1 Entity Details | 10 days | Thu 22/5/14 | Wed 4/6/14 | 104 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.1.2.2. User Groups | 10 days | Mon 2/3/15 | Fri 13/3/15 | 105 | India | 100%
Manually Scheduled | 5.1.2.3 User | 10 days | Fri 27/2/15 | Thu 12/3/15 | 106 | India | 100%
Manually Scheduled | 5.1.2.4 Department Master | 10 days | Fri 13/2/15 | Thu 26/2/15 | 107 | India | 100%
Manually Scheduled | 5.1.2.5 Password Setup | 10 days | Fri 6/2/15 | Thu 19/2/15 | 108 | India | 100%
Manually Scheduled | 5.1.2.6 Release Locked Users | 10 days | Fri 6/2/15 | Thu 19/2/15 | 109 | India | 100%
Manually Scheduled | 5.1.2.7 Country for User Access | 10 days | Fri 13/2/15 | Thu 26/2/15 | 110 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.1.3 Service Provider | 15 days | Wed 19/11/14 | Tue 9/12/14 |  | India | 100%
Manually Scheduled | 5.1.3.1 Insurer Master | 10 days | Wed 19/11/14 | Tue 2/12/14 | 112 | India | 100%
Manually Scheduled | 5.1.3.2 Surveyor Master | 10 days | Wed 19/11/14 | Tue 2/12/14 | 113 | India | 100%
Manually Scheduled | 5.1.3.3 Lawyer Master | 10 days | Wed 19/11/14 | Tue 2/12/14 | 114 | India | 100%
Manually Scheduled | 5.1.3.4 Workshop/Dept Master | 10 days | Tue 25/11/14 | Mon 8/12/14 | 115 | India | 100%
Manually Scheduled | 5.1.3.5 Hospital Master | 10 days | Wed 26/11/14 | Tue 9/12/14 | 116 | India | 100%
Manually Scheduled | 5.1.3.6 Adjuster Master | 10 days | Tue 25/11/14 | Mon 8/12/14 | 117 | India | 100%
Manually Scheduled | 5.1.4 Nature Of Loss | 10 days | Wed 25/6/14 | Tue 8/7/14 | 118 | India | 100%
Manually Scheduled | 5.1.5 Type of Loss | 10 days | Wed 18/6/14 | Tue 1/7/14 | 119 | India | 100%
Manually Scheduled | 5.1.6 Main Class Business | 10 days | Wed 18/6/14 | Tue 1/7/14 | 120 | India | 100%
Manually Scheduled | 5.1.7 Sub Class | 10 days | Wed 18/6/14 | Tue 1/7/14 | 121 | India | 100%
Manually Scheduled | 5.1.8 Claims Expense Master | 10 days | Wed 18/6/14 | Tue 1/7/14 | 122 | India | 100%
Manually Scheduled | 5.1.9 Claims Close Reason Master | 10 days | Wed 18/6/14 | Tue 1/7/14 | 123 | India | 100%
Manually Scheduled | 5.1.10 Currency Master | 10 days | Wed 18/6/14 | Tue 1/7/14 | 124 | India | 100%
Manually Scheduled | 5.1.11 Exchange Rate Master | 10 days | Wed 18/6/14 | Tue 1/7/14 | 125 | India | 100%
Manually Scheduled | 5.1.12 Vehicle Class | 10 days | Wed 18/6/14 | Tue 1/7/14 | 126 | India | 100%
Manually Scheduled | 5.1.13 Vehicle Make | 10 days | Wed 18/6/14 | Tue 1/7/14 | 127 | India | 100%
Manually Scheduled | 5.1.14 Vehicle Model | 10 days | Wed 18/6/14 | Tue 1/7/14 | 128 | India | 100%
Manually Scheduled | 5.1.15 Insurance Policy | 10 days | Wed 25/6/14 | Tue 8/7/14 | 129 | India | 100%
Manually Scheduled | 5.1.16 GST Setting | 10 days | Wed 18/6/14 | Tue 1/7/14 | 130 | India | 100%
Manually Scheduled | 5.1.17 Organization | 10 days | Mon 12/1/15 | Fri 23/1/15 | 131 | India | 100%
Manually Scheduled | 5.1.18 Claim Officer Duty | 10 days | Wed 17/9/14 | Tue 30/9/14 | 132 | India | 100%
Manually Scheduled | 5.1.19 LOU Rate | 10 days | Wed 24/9/14 | Tue 7/10/14 | 133 | India | 100%
Manually Scheduled | 5.1.20 Interchange | 10 days | Wed 24/9/14 | Tue 7/10/14 | 134 | India | 100%
Manually Scheduled | 5.1.21 Deductible | 10 days | Mon 29/12/14 | Fri 9/1/15 | 135 | India | 98%
Manually Scheduled | 5.1.22 User Manual | 30 days | Mon 2/2/15 | Fri 13/3/15 |  | India | 100%
Manually Scheduled | 5.1.23 Test Approach/Test Cases | 5 days | Mon 2/2/15 | Fri 6/2/15 |  | India | 100%
Manually Scheduled | 5.1.24 QA Testing | 20 days | Wed 11/2/15 | Tue 10/3/15 |  | India | 100%
Manually Scheduled | 5.1.25 UAT | 20 days | Tue 10/3/15 | Mon 6/4/15 |  | Singapore | 50%
Manually Scheduled | 5.2 Upload | 58 days | Fri 30/1/15 | Tue 21/4/15 | 136 | India | 33%
Manually Scheduled | 5.2.1 TAC Upload | 25 days | Thu 26/2/15 | Wed 1/4/15 | 137 | India | 100%
Manually Scheduled | 5.2.2 Claim File Upload | 25 days | Thu 26/2/15 | Wed 1/4/15 | 138 | India | 85%
Manually Scheduled | 5.2.3 SAP File Upload | 25 days | Thu 26/2/15 | Wed 1/4/15 | 139 | India | 0% | Phase 2 delivery | Phase 2 delivery
Manually Scheduled | 5.2.4 User Manual | 5 days | Thu 2/4/15 | Wed 8/4/15 | 234 | India | 50%
Manually Scheduled | 5.2.5 Test Approach/Test Cases | 2 days | Wed 1/4/15 | Thu 2/4/15 | 139 | India | 100%
Manually Scheduled | 5.2.6 QA Testing | 5 days | Wed 1/4/15 | Tue 7/4/15 | 139 | Singapore | 0%
Manually Scheduled | 5.2.7 UAT | 10 days | Wed 8/4/15 | Tue 21/4/15 |  | CDGI | 0%
Manually Scheduled | 5.3 Claim | 179 days | Fri 14/11/14 | Wed 22/7/15 |  | India | 33%
Manually Scheduled | 5.3.1 Buses | 92 days | Fri 14/11/14 | Mon 23/3/15 | 141 | India | 55%
Manually Scheduled | 5.3.1.1 Accident | 10 days | Fri 14/11/14 | Thu 27/11/14 | 142 | India | 100%
Manually Scheduled | 5.3.1.2 Claim | 12 days | Fri 14/11/14 | Mon 1/12/14 | 143 | India | 100%
Manually Scheduled | 5.3.1.3 Service Provider | 15 days | Fri 14/11/14 | Thu 4/12/14 | 144 | India | 100%
Manually Scheduled | 5.3.1.4 Notes | 10 days | Fri 14/11/14 | Thu 27/11/14 | 145 | India | 100%
Manually Scheduled | 5.3.1.5 Tasks | 12 days | Fri 14/11/14 | Mon 1/12/14 | 146 | India | 100%
Manually Scheduled | 5.3.1.6 Attachment | 12 days | Fri 14/11/14 | Mon 1/12/14 | 147 | India | 100%
Manually Scheduled | 5.3.1.7 Dairy | 20 days | Fri 14/11/14 | Thu 11/12/14 | 148 | India | 100%
Manually Scheduled | 5.3.1.8 Reassigned Dairy | 10 days | Fri 14/11/14 | Thu 27/11/14 | 149 | India | 100%
Manually Scheduled | 5.3.1.9 Reserve | 10 days | Fri 2/1/15 | Thu 15/1/15 | 150 | India | 58%
Manually Scheduled | 5.3.1.10 Reserve History | 5 days | Fri 16/1/15 | Thu 22/1/15 | 249 | India | 0%
Manually Scheduled | 5.3.1.11 Mandate | 30 days | Fri 2/1/15 | Thu 12/2/15 | 152 | India | 19%
Manually Scheduled | 5.3.1.12 Mandate History | 5 days | Fri 16/1/15 | Thu 22/1/15 | 251 | India | 0% | Waiting for functionality
Manually Scheduled | 5.3.1.13 Payment | 30 days | Mon 19/1/15 | Fri 27/2/15 | 154 | India | 0% | Waiting for functionality
Manually Scheduled | 5.3.1.14 Payment History | 5 days | Mon 2/3/15 | Fri 6/3/15 | 253 | India | 0% | Waiting for functionality
Manually Scheduled | 5.3.1.15 Recovery | 30 days | Tue 10/2/15 | Mon 23/3/15 | 156 | India | 0%
Manually Scheduled | 5.3.1.16 Transaction History | 38 days | Thu 30/10/14 | Mon 22/12/14 | 157 | India | 100%
Manually Scheduled | 5.3.1.17 Alert Indicator for Deductible |  |  |  |  | India | 0%
Manually Scheduled | 5.3.2 Trains | 127 days | Fri 14/11/14 | Mon 11/5/15 | 159 | India | 32%
Manually Scheduled | 5.3.3 Taxis | 30 days | Tue 7/4/15 | Mon 18/5/15 | 160 | India | 0% | Waiting for functionality
Manually Scheduled | 5.3.4 Rental Cars | 30 days | Fri 8/5/15 | Thu 18/6/15 | 161 | India | 0% | Waiting for functionality
Manually Scheduled | 5.3.5 Private Cars | 30 days | Fri 8/5/15 | Thu 18/6/15 | 162 | India | 0% | Waiting for functionality
Manually Scheduled | 5.3.6 User Manual | 30 days | Mon 11/5/15 | Fri 19/6/15 |  | India | 0% | Waiting for functionality
Manually Scheduled | 5.3.7 Test Approach/Test Cases | 5 days | Fri 22/5/15 | Thu 28/5/15 |  | India | 0%
Manually Scheduled | 5.3.8 QA Testing | 25 days | Thu 28/5/15 | Wed 1/7/15 |  | Singapore | 0%
Manually Scheduled | 5.3.9 UAT | 15 days | Thu 2/7/15 | Wed 22/7/15 | 264 | CDGI | 0%
Manually Scheduled | 5.4 Dashboard | 34 days | Thu 12/2/15 | Tue 31/3/15 |  | India | 8% | Waiting for functionality
Manually Scheduled | 5.4.1 Sections of Dashboard per User Group | 10 days | Thu 12/2/15 | Wed 25/2/15 |  | India | 50% | pending for requirement detail | waiting To Get Details
Manually Scheduled | 5.4.2 User Manual | 10 days | Thu 26/2/15 | Wed 11/3/15 | 267 | India | 0%
Manually Scheduled | 5.4.3 Test Approach/Test Cases | 5 days | Thu 26/2/15 | Wed 4/3/15 | 267 | India | 0%
Manually Scheduled | 5.4.4 QA Testing | 2 days | Thu 26/2/15 | Fri 27/2/15 | 267 | Singapore | 0%
Manually Scheduled | 5.4.5 UAT | 5 days | Thu 12/3/15 | Wed 18/3/15 | 268 | CDGI | 0%
Manually Scheduled | 5.5 Diary Listing | 27 days | Tue 24/2/15 | Wed 1/4/15 |  | India | 100%
Manually Scheduled | 5.5.1 Diary Items | 10 days | Tue 24/2/15 | Mon 9/3/15 | 166 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.5.2 Assigned Tasks | 10 days | Tue 24/2/15 | Mon 9/3/15 | 167 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.5.3 Escalation Tasks | 17 days | Tue 24/2/15 | Wed 18/3/15 | 168 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.5.4 User Manual | 5 days | Thu 19/3/15 | Wed 25/3/15 | 275 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.5.5 Test Approach/Test Cases | 5 days | Thu 26/3/15 | Wed 1/4/15 | 276 | India | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.5.6 QA Testing | 5 days | Thu 26/3/15 | Wed 1/4/15 | 276 | Singapore | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.5.7 UAT | 5 days | Wed 25/3/15 | Tue 31/3/15 | 276 | CDGI | 100% | Requirement revoked and menu removed from Application
Manually Scheduled | 5.6 Claim Enquiry | 67 days | Wed 11/3/15 | Thu 11/6/15 | 169 | India | 29%
Manually Scheduled | 5.6.1 Claims | 15 days | Thu 12/3/15 | Wed 1/4/15 | 170 | India | 100%
Manually Scheduled | 5.6.2 Claim Documents Printing | 10 days | Fri 1/5/15 | Thu 14/5/15 | 171 | India | 100%
Manually Scheduled | 5.6.3 Job Schedule Enquiry | 10 days | Fri 15/5/15 | Thu 28/5/15 | 282 | India | 100%
Manually Scheduled | 5.6.4 User Manual | 5 days | Fri 29/5/15 | Thu 4/6/15 | 283 | India | 0%
Manually Scheduled | 5.6.5 Test Approach/Test Cases | 5 days | Fri 29/5/15 | Thu 4/6/15 | 283 | India | 0%
Manually Scheduled | 5.6.6 QA Testing | 5 days | Fri 29/5/15 | Thu 4/6/15 | 283 | Singapore | 0%
Manually Scheduled | 5.6.7 UAT | 5 days | Fri 5/6/15 | Thu 11/6/15 | 284 | CDGI | 0%
Manually Scheduled | 5.7 Document Generation Module | 27 days | Thu 23/4/15 | Fri 29/5/15 |  | India | 0% | Waiting for functionality
Manually Scheduled | 5.8 Document Print | 25 days | Wed 6/5/15 | Tue 9/6/15 |  | India | 0%
Manually Scheduled | 5.9 Unreported Claim Menu | 49 days | Fri 30/1/15 | Wed 8/4/15 |  | India | 100%
Manually Scheduled | 5.9.1 UI and functionality implementation | 10 days | Thu 19/2/15 | Wed 4/3/15 | 178 | India | 100% | similar to 5.3 Claim task and need to be strike through
Manually Scheduled | 5.9.2 User Manual | 10 days | Thu 5/3/15 | Wed 18/3/15 | 302 | India | 100% | similar to 5.3 Claim task and need to be strike through
Manually Scheduled | 5.9.3 Test Approach/Test Cases | 5 days | Thu 19/3/15 | Wed 25/3/15 | 302 | India | 100% | similar to 5.3 Claim task and need to be strike through
Manually Scheduled | 5.9.4 QA Testing | 5 days | Thu 19/3/15 | Wed 25/3/15 | 303 | Singapore | 100% | similar to 5.3 Claim task and need to be strike through
Manually Scheduled | 5.9.5 UAT | 10 days | Thu 26/3/15 | Wed 8/4/15 | 303 | CDGI | 100% | similar to 5.3 Claim task and need to be strike through
Manually Scheduled | 5.10 Security Management System | 86 days | Mon 1/12/14 | Mon 30/3/15 |  | India | 31% | similar to 5.3 Claim task and need to be strike through
Auto Scheduled | 5.11 New Requirement - New Master Tables | 49 days | Tue 3/3/15 | Fri 8/5/15 |  |  | 0%
Manually Scheduled | 5.11.1 iTrack #2 | 39 days | Tue 3/3/15 | Fri 24/4/15 |  |  | 80%
Manually Scheduled | 5.11.2 User Manual | 6 days | Tue 28/4/15 | Tue 5/5/15 |  |  | 0%
Manually Scheduled | 5.11.3 Test Approach/Test Cases | 3 days | Fri 24/4/15 | Tue 28/4/15 |  |  | 0%
Manually Scheduled | 5.11.4 QA Testing | 3 days | Tue 28/4/15 | Thu 30/4/15 |  |  | 0%
Manually Scheduled | 5.11.5 UAT | 4 days | Tue 5/5/15 | Fri 8/5/15 |  |  | 0%
Auto Scheduled | 5.12 New Requirement - LOG Request | 49 days | Tue 3/3/15 | Fri 8/5/15 |  |  | 0%
Manually Scheduled | 5.12.1 iTrack #10 | 39 days | Tue 3/3/15 | Fri 24/4/15 |  |  | 80%
Manually Scheduled | 5.12.2 User Manual | 6 days | Tue 28/4/15 | Tue 5/5/15 |  |  | 0%
Manually Scheduled | 5.12.3 Test Approach/Test Cases | 3 days | Fri 24/4/15 | Tue 28/4/15 |  |  | 0%
Manually Scheduled | 5.12.4 QA Testing | 3 days | Tue 28/4/15 | Thu 30/4/15 |  |  | 0%
Manually Scheduled | 5.12.5 UAT | 4 days | Tue 5/5/15 | Fri 8/5/15 |  |  | 0%
Auto Scheduled | 5.13 New Requirement - FAL Masters | 49 days | Tue 3/3/15 | Fri 8/5/15 |  |  | 0%
Manually Scheduled | 5.13.1 iTrack #23 | 39 days | Tue 3/3/15 | Fri 24/4/15 |  |  | 70%
Manually Scheduled | 5.13.2 User Manual | 6 days | Tue 28/4/15 | Tue 5/5/15 |  |  | 0%
Manually Scheduled | 5.13.3 Test Approach/Test Cases | 3 days | Fri 24/4/15 | Tue 28/4/15 |  |  | 0%
Manually Scheduled | 5.13.4 QA Testing | 3 days | Tue 28/4/15 | Thu 30/4/15 |  |  | 0%
Manually Scheduled | 5.13.5 UAT | 4 days | Tue 5/5/15 | Fri 8/5/15 |  |  | 0%
Manually Scheduled | 6 QA Test Scripts | 20 days | Thu 23/7/15 | Wed 19/8/15 | 189 | India | 0%
Manually Scheduled | 7 QA Testing | 20 days | Wed 9/9/15 | Tue 6/10/15 | 335 | India | 0%
Manually Scheduled | 8 End-to-end UAT | 20 days | Wed 7/10/15 | Tue 3/11/15 | 338 | Singapore | 0%
Manually Scheduled | 9 Client UAT | 20 days | Wed 7/10/15 | Tue 3/11/15 |  | CDGI | 0%
Manually Scheduled | 10 Deployment | 26 days | Wed 4/11/15 | Wed 9/12/15 |  | Singapore | 0%