## 30 March 2015
S.no. | Task | Work completed | India Ebix Remarks
1 | 4.1.2.1 Entity Details | 100% | Requirement revoked and menu removed from Application
2 | 4.1.2.2. User Groups | 100%
3 | 4.1.2.3 User | 100%
4 | 4.1.2.4 Department Master | 100%
5 | 4.1.2.5 Password Setup | 100%
6 | 4.1.2.6 Release Locked Users | 100%
7 | 4.1.2.7 Country for User Access | 100% | Requirement revoked and menu removed from Application
8 | 4.1.17 Organization | 100%
9 | 4.2.1 TAC Upload | 100%
10 | 4.2.2 Claim File Upload | 100%
11 | 4.4.1 Sections of Dashboard as per User Group | 80%
12 | 4.5 Diary Listing | 100% | Requirement revoked and menu removed from Application
13 | 4.5.1 Diary Items | 100% | Requirement revoked and menu removed from Application
14 | 4.5.2 Assigned Tasks | 100% | Requirement revoked and menu removed from Application
15 | 4.5.3 Escalation Tasks | 100% | Requirement revoked and menu removed from Application
16 | 4.6 Claim Enquiry | 100%
17 | 4.6.1 Claims | 100%
18 | 4.6.2 Claim Documents Printing | 100%
19 | 4.6.3 Job Schedule Enquiry | 100%
20 | 5.1.2.1 Entity Details | 100% | Requirement revoked and menu removed from Application
21 | 5.1.2.2. User Groups | 100%
22 | 5.1.2.3 User | 100%
23 | 5.1.2.4 Department Master | 100%
24 | 5.1.2.5 Password Setup | 100%
25 | 5.1.2.6 Release Locked Users | 100%
26 | 5.1.2.7 Country for User Access | 100% | Requirement revoked and menu removed from Application
27 | 5.1.17 Organization | 100%
28 | 5.1.22 User Manual | 100%
29 | 5.1.23 Test Approach/Test Cases | 100%
30 | 5.1.24 QA Testing | 100%
31 | 5.1.25 UAT | 0% | Provide Response and Fill percentage Completed
32 | 5.2.1 TAC Upload | 100%
33 | 5.2.2 Claim File Upload | 85
34 | 5.2.5 Test Approach/Test Cases | 90
35 | 5.3.1.10 Reserve History | 100%
36 | 5.4.1 Sections of Dashboard per User Group | 50
37 | 5.5 Diary Listing | 100% | Requirement revoked and menu removed from Application
38 | 5.5.1 Diary Items | 100% | Requirement revoked and menu removed from Application
39 | 5.5.2 Assigned Tasks | 100% | Requirement revoked and menu removed from Application
40 | 5.5.3 Escalation Tasks | 100% | Requirement revoked and menu removed from Application
41 | 5.5.4 User Manual | 100% | Requirement revoked and menu removed from Application
42 | 5.5.5 Test Approach/Test Cases | 100% | Requirement revoked and menu removed from Application
43 | 5.5.6 QA Testing | 100% | Requirement revoked and menu removed from Application
44 | 5.5.7 UAT | 100% | Requirement revoked and menu removed from Application
45 | 5.6.1 Claims | 100%
46 | 5.6.2 Claim Documents Printing | 100%
47 | 5.6.3 Job Schedule Enquiry | 100%
48 | 5.9 Unreported Claim Menu | 100% | similar to 5.3 Claim task and need to be strike through
49 | 5.9.1 UI and functionality implementation | 100% | similar to 5.3 Claim task and need to be strike through
50 | 5.9.2 User Manual | 100% | similar to 5.3 Claim task and need to be strike through
51 | 5.9.3 Test Approach/Test Cases | 100% | similar to 5.3 Claim task and need to be strike through
52 | 5.9.4 QA Testing | 100% | similar to 5.3 Claim task and need to be strike through
53 | 5.9.5 UAT | 100% | similar to 5.3 Claim task and need to be strike through
54 | 5.7.2 User Manual | 100%
55 | 5.7.3 Test Approach/Test Cases | 100%