## List of Requirments
S.no. | Modules | Requirements | Feedback
1 | Claim Recovery Module | We require UI and Data elements information that needs to be inserted in Claim Recovery screen . | 22-Jul-14: Document has been sent.
2 | claim payment Document Enquiry | We require Claim payment document screen layout and Data element to be inserted in it . | 22-Jul-14: This is currently being worked on
3 | Document Generation | We Need to know Trigger points for generation of each form as by going through contents of forms it seems that they should be generated at different – 2 events : For an example : 1) DV (Individuals) 2) DV (Infant) Probable Triggering event : Payment of claim Above forms are having same format but generation of these forms will depend on a condition of whether insured is infant or in “conscious state” So there are following conditions needs to be discussed and confirmed by client : 1) Triggering event for generation of form 2) In case of multiple forms having same format but dependent on particular case such as “ insured is infant or in conscious state . | 22-Jul-14: This will be discussed with CDGI during the meeting
4 | Forms with multiple sheets Form name : payment request minutes ( latest ) : Location path : Defence → F →payment process→Payment Request Minutes ( latest ) | Some of the forms are in Excel format having multiple sheets . For an example “ payment request minutes ( latest )“ having 8 sheets so can we just generate two forms for this as only two formats are being used in the sheets ? 1) Min format 2) Facsimile Transmission Requirement : 1) For all forms which are in excel format we need to know , how do we proceed for generation of form. This Form Contains total 8 worksheet : 1) MR-CGH : Contains Min5 and Facsimile Transmission 2) Public liab : Min 3) Injury : Min and Facsimile transmission 4) MR TTSH : Min and Facsimile transmission 5) Medisave : Min and Facsimile Transmission 6) III DN : Min 1 7) Property Payment : MIN 8) Payment summary : report | 22-Jul-14: This will be discussed with CDGI during the meeting
5 | Claim registration → 1st party claimant | In Case of own damage , from where we will have first claimant name and address information ? Currently claimant name and address information is being asked in “3rd party tab” only | 22-Jul-14: If it is Own Damages, the System should pick up the First Claimant Name and Address Information from the Organization Dropdown list, e.g. Citycab, SBS Transit, Comfort Taxi & SMRT
6 | Claim Status | Please provide us abbreviation of claim status “ f “ And please Confirm following abbreviations C = complete I = Incomplete
7 | Task Tab | Task tab already present on new claim registration . We require UI and Data elements information that needs to be inserted in this tab.
8 | Notes | Notes tab already present on new claim registration . We require UI and Data elements information that needs to be inserted in Notes tab | 24-Jul-14: Free text box. Serial Numbered with Save button and date and Time. Please see attachment (same as Transaction Tabs)
9 | Transaction tabs | Transaction tabs already present on new claim registration . We require UI and Data elements information that needs to be inserted in these. | 24-Jul-14: Please see attachment
10 | Accident screen | Please confirm following : “ Location of accident “ field required on accident tab as currently we dont have any such field for getting this information . “Fact” text box Is required for getting details of accident . | 22-Jul-14: Agree. There will be more fields that will need to be added after discussion with CDGI on the documents mapping
11 | User Admin : Email box | Can we have Email input box at user master? On Diary Re-assignment we need to send email to both “ original user “ and “ new user “ , but we dont have Email box for getting the details . | 22-Jul-14: Agree. There will be more fields that will need to be added after discussion with CDGI on the documents mapping
12 | Finance Tab |  | 22-Jul-14: A Document was sent on the screen layout and fields required for this Tab. Some of these fields will be required for the document mapping especially the Finance Breakdown.

## Project status
New Requirements/Changes
Project : MCAS
S.NO. | TFS ID | Requirement / Issue | Description | Status ( 15 july 2014 ) | Target Date | Remarks | 17 july 2014 EOD status | 21 july 2014
1 | 13670 Parent id is 13302 | Add button Labeled as 'View Reserve History'. | Location of button: New claim registration menu → Claim tab → Initial Reserve frame → Besides Total reserve label. Output : Reserve History button should show , Reserve history against claimant in descending order ( latest to oldest date ) | PENDING | 2014-07-17 |  |  | Completed
2 | 13671 Parent id is 13303 | Following four options needed to add in Drop down list labeled as 'Payable To'. | i) Claimant ii) Third Party Adjuster iii) Third Party Lawyer iv) Third Party workshop Location: New claim registration menu → 3rd Party tab → claim Amount/ Payout frame → Payable to drop down list. | PENDING | 2014-07-16 | 17-Jul-14: Not Done | Completed
3 | 13339, | Text of Labels need to be change | I) Current Transaction Reserve change into “Reserve Movement “ ii) Reserve Movement change into “Current Reserve “ Location: Under Reserve tab | Completed , please verify |  | Done
4 | 13339, | Add one button under “Reserve tab” labeled as “View Reserve History “. | Note: By clicking on this button , Reserve History of all the claimant need to be displayed in date wise in descending order. | Completed |  | Done
5 | 13672 Parent id : 13339 | Add one button under “Payment tab” labeled as “View Payment History “. | Note : By clicking on this button , Payment History of all claimant need to be displayed in date wise in descending order. | Completed |  | Done
6 | 13339 | Add options in drop down list: | Drop down list label = 'Payee type' List values: 1) Workshop, 2) Adjuster, 3) Lawyer, 4) Claimant. Location: Under Payment tab | Completed |  | Done
7 | 13339 | Remove one Drop down list, labeled as 'Category'. | Location: Under Payment tab | completed |  | Done
8 | 13339 | Location of Payee need to be replace with removed 'Category' and the text box need to be enlarged . | Location: Under Payment tab | completed |  | Done
9 | 13339 | Payment Due date needed to be shifted upward. | Location: Under Payment tab | completed |  | Done
10 | 13339, | All labeled text as ' Base' needed to be changed as ' Local '. | Location: Under all tab wherever applicable | completed |  | Done
11 | 13673 Parent id is 13303 | Text boxes size need to be re sized under 3rd party tab , in Initial Reserve frame. | Reserve Ex. Rate Upto digits mentioned Expense Ex. Rate Upto digits mentioned Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Pending | 2014-07-16 | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated | completed
12 | 13673 Parent id is 13303 | Text boxes size need to be re sized under 3rd party tab , in 'Claim Amount / Payout' frame. | SGD Upto digits mentioned Claim Amount ` Ex. Rate Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Pending | 2014-07-16 | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated | completed
13 | 13674 | In Claim Adjustments menu: user can change reserves only and other tabs will be view only. |  | Pending * other tabs can be changed * claimant not coming on reserve tab | 2014-07-17 |  |  | Completed
14 | 13675 | In Claim Inquiry Menu: All tabs needed to be view only , user cant change in this menu. |  | Pending | 2014-07-17 |  |  | Completed
15 | 13676 | In Claim Payment Menu: | I) Remove Incomplete claims menu completely II) In Claim Payment processing Menu : User can make only payment , other tabs will be for view only, no changes can be made in other tabs information. | 1) Completed 2)Pending | 2014-07-16 | Done | completed
16 |  | In System Admin Menu: | Complete Office Duty Roster | Completed | 2014-07-16 |  | completed
17 |  | In New Claim Registration: | a. Tasks - Layout and page elements need to be discussed. | Pending | a) |  | Meeting required to understand Task tab | Functionality of Tasks tab Needs to be discussed
18 |  |  | b. Diary Reassignment – Partly done, may need discussion. Email functionality pending, will be completed by 18 July 14. | Pending | b) 18-Jul-14 |  | b) Meeting Required * Need to discuss and confirm Layout and page elements of diary reassignment which is already created | Diary re-assignment page is now opening and now we are able to save diary
19 |  |  | c. Document Preview – 18 July 14 (only view of doc as per template- data element mapping is in progress). We need more discussion for clear understanding of trigger point of document generation. | Pending | c) 18-Jul-14 |  | c) Meeting Required We need to know the triggering point of each document generation as currently all forms are generating on new claim registration tab | * 20 forms has been verified and doubts has been noted out Meeting request has been sent for unknown and unmapped fields in forms
20 |  |  | d. Complete Claim Functionality - 17 July 14. | Pending | d) 17-Jul-14 |  | In progress | we are able to complete claim and also the list of completed claim is coming under claim payment processing for making payments
21 |  |  | e. Claim Reserve Tab – UI has been delivered. Processing is in progress and may require further discussion. | Pending |  |  |  | * Claim reserve tab is working
22 |  |  | f. Claim Payment Tab – UI has been delivered. Processing is in progress and may require further discussion. | Pending |  |  |  | * Payment tab Is working We need to finalize payment tab work flow , We Need to know if any gaps are there on page with actual requirement or not
23 |  | In Claim Payment: | a. Claim Payment Processing – flow will be completed by 21 July 14. We need discussion on it. b. Claim Payment Document Enquiry – need to finalize the UI layout for this menu. | a) Pending b) Pending | a) 21-Jul-14 |  | Claim procession discussion meeting required | * Claim payment tab working , workflow testing is pending
24 |  | In Claim Recovery: | Need to understand Requirement | Pending |  |  | Meeting required | * Meeting request has been sent on 17th july asking for UI information of claim Recovery
25 |  | In Claim Enquiry: | Need to understand Requirement | Pending |  |  | Meeting required | under process as we got details on 21sth july In case of doubts we will call for meeting
26 |  | In Whole System: | Suggestion: Any fields that require User to input Yes / No to have Radio Button Selection instead of Dropdown |  |  | 17-Jul-14: Suggestion | Under Review