## List of Requirments
S.no. | Modules | Requirements | Feedback | Query raised on 24 July 2014 | Feedback
1 | Claim Recovery Module | We require UI and Data elements information that needs to be inserted in Claim Recovery screen . | 22-Jul-14: Document has been sent.
2 | claim payment Document Enquiry | We require Claim payment document screen layout and Data element to be inserted in it . | 22-Jul-14: This is currently being worked on
3 | Document Generation | We Need to know Trigger points for generation of each form as by going through contents of forms it seems that they should be generated at different – 2 events : For an example : 1) DV (Individuals) 2) DV (Infant) Probable Triggering event : Payment of claim Above forms are having same format but generation of these forms will depend on a condition of whether insured is infant or in “conscious state” So there are following conditions needs to be discussed and confirmed by client : 1) Triggering event for generation of form 2) In case of multiple forms having same format but dependent on particular case such as “ insured is infant or in conscious state . | 22-Jul-14: This will be discussed with CDGI during the meeting
4 | Forms with multiple sheets Form name : payment request minutes ( latest ) : Location path : Defence → F →payment process→Payment Request Minutes ( latest ) | Some of the forms are in Excel format having multiple sheets . For an example “ payment request minutes ( latest )“ having 8 sheets so can we just generate two forms for this as only two formats are being used in the sheets ? 1) Min format 2) Facsimile Transmission Requirement : 1) For all forms which are in excel format we need to know , how do we proceed for generation of form. This Form Contains total 8 worksheet : 1) MR-CGH : Contains Min5 and Facsimile Transmission 2) Public liab : Min 3) Injury : Min and Facsimile transmission 4) MR TTSH : Min and Facsimile transmission 5) Medisave : Min and Facsimile Transmission 6) III DN : Min 1 7) Property Payment : MIN 8) Payment summary : report | 22-Jul-14: This will be discussed with CDGI during the meeting
5 | Claim registration → 1st party claimant | In Case of own damage , from where we will have first claimant name and address information ? Currently claimant name and address information is being asked in “3rd party tab” only | 22-Jul-14: If it is Own Damages, the System should pick up the First Claimant Name and Address Information from the Organization Dropdown list, e.g. Citycab, SBS Transit, Comfort Taxi & SMRT
6 | Claim Status | Please provide us abbreviation of claim status “ f “ And please Confirm following abbreviations C = complete I = Incomplete
7 | Task Tab | Task tab already present on new claim registration . We require UI and Data elements information that needs to be inserted in this tab.
8 | Notes | Notes tab already present on new claim registration . We require UI and Data elements information that needs to be inserted in Notes tab | 24-Jul-14: Free text box. Serial Numbered with Save button and date and Time. Please see attachment (same as Transaction Tabs) | Do we need to delete screen which comes when user click on “ add new note “ button ? And apply your changes ? | 25-Jul-14: Yes. The screen is to be deleted
9 | Transaction tabs | Transaction tabs already present on new claim registration . We require UI and Data elements information that needs to be inserted in these. | 24-Jul-14: Please see attachment | Is this the part of transaction tab which is coming right now or we need to create Transaction history tab for the screen you provided ?
10 | Accident screen | Please confirm following : “ Location of accident “ field required on accident tab as currently we dont have any such field for getting this information . “Fact” text box Is required for getting details of accident . | 22-Jul-14: Agree. There will be more fields that will need to be added after discussion with CDGI on the documents mapping
11 | User Admin : Email box | Can we have Email input box at user master? On Diary Re-assignment we need to send email to both “ original user “ and “ new user “ , but we dont have Email box for getting the details . | 22-Jul-14: Agree. There will be more fields that will need to be added after discussion with CDGI on the documents mapping
12 | Finance Tab |  | 22-Jul-14: A Document was sent on the screen layout and fields required for this Tab. Some of these fields will be required for the document mapping especially the Finance Breakdown. | finance tab working please check and confirm on incomplete claim menu screen | 25-Jul-14: How do we activate the Finance Tab? It is grayed out on all the current Claims

## Project status
New Requirements/Changes
Project : MCAS
S.NO. | TFS ID | Module | Requirement / Issue Description | Current status | Target Date | Date wise activity description | Remarks
1 | 13670 Parent id is 13302 | Claim screen : Add button Labeled as 'View Reserve History'. | Location of button: New claim registration menu → Claim tab → Initial Reserve frame → Besides Total reserve label. Output : Reserve History button should show , Reserve history against claimant in descending order ( latest to oldest date ) | Completed | 2014-07-17 | 15th July 2014 : PENDING 17th July 2014 : Completed
2 | 13671 Parent id is 13303 | 3rd party screen : Following four options needed to add in Drop down list labeled as 'Payable To'. | i) Claimant ii) Third Party Adjuster iii) Third Party Lawyer iv) Third Party workshop Location: New claim registration menu → 3rd Party tab → claim Amount/ Payout frame → Payable to drop down list. | Completed | 2014-07-16 | 17th July 2014 : Completed | 17-Jul-14: Not Done
3 | 13339, | Text of Labels need to be change | I) Current Transaction Reserve change into “Reserve Movement “ ii) Reserve Movement change into “Current Reserve “ Location: Under Reserve tab | Completed |  | 17th July 2014 : Completed | Done
4 | 13339, | Add one button under “Reserve tab” labeled as “View Reserve History “. | Note: By clicking on this button , Reserve History of all the claimant need to be displayed in date wise in descending order. | Completed |  | 17th July 2014 : Completed | Done
5 | 13672 Parent id : 13339 | Add one button under “Payment tab” labeled as “View Payment History “. | Note : By clicking on this button , Payment History of all claimant need to be displayed in date wise in descending order. | Completed |  | 17th July 2014 : Completed | Done
6 | 13339 | Add options in drop down list: | Drop down list label = 'Payee type' List values: 1) Workshop, 2) Adjuster, 3) Lawyer, 4) Claimant. Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
7 | 13339 | Remove one Drop down list, labeled as 'Category'. | Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
8 | 13339 | Location of Payee need to be replace with removed 'Category' and the text box need to be enlarged . | Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
9 | 13339 | Payment Due date needed to be shifted upward. | Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
10 | 13339, | All labeled text as ' Base' needed to be changed as ' Local '. | Location: Under all tab wherever applicable | Completed |  | 17th July 2014 : Completed | Done
11 | 13673 Parent id is 13303 | Reserve screen : Text boxes size need to be re sized under 3rd party tab , in Initial Reserve frame. | Reserve Ex. Rate Upto digits mentioned Expense Ex. Rate Upto digits mentioned Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Completed | 2014-07-16 | 17th July 2014 : Completed | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
12 | 13673 Parent id is 13303 | Reserve Screen : Text boxes size need to be re sized under 3rd party tab , in 'Claim Amount / Payout' frame. | SGD Upto digits mentioned Claim Amount ` Ex. Rate Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Completed | 2014-07-16 | 17th July 2014 : Completed | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
13 | 13674 | Claim Adjustments menu : | Requirement to make all tabs non editable except reserve tab | Completed | 2014-07-17 | 17th July 2014 : Completed
14 | 13675 | In Claim Inquiry Menu: | * Requirement to make all tabs non editable | Completed | 2014-07-17 | 17th July 2014 : Completed
15 | 13676 | In Claim Payment Menu: | I) Remove Incomplete claims menu completely II) In Claim Payment processing Menu : User can make only payment , other tabs will be for view only, no changes can be made in other tabs information. | Completed | 2014-07-16 | 17th July 2014 : Completed | Done
16 | 13321 | In System Admin Menu: | Complete Office Duty Roster | Completed | 2014-07-16 | 17th July 2014 : Completed
17 | - | In New Claim Registration: | Tasks - Layout and page elements need to be discussed. | Doubts shared / Waiting to get the details | a) | 17th July 2014 : Meeting required to understand Task tab 21st July 2014 : Functionality of Tasks tab Needs to be discussed 23rd July 2014 Waiting to get the details : Requirements has been shared on 22nd July
18 | 13517 | Diary Reassignment | Partly done, may need discussion. Email functionality pending, will be completed by 18 July 14. | Doubts shared / Waiting to get the details | b) 18-Jul-14 | 17th July 2014 : Meeting Required * Need to discuss and confirm Layout and page elements of diary reassignment which is already created 21st July 2014: Diary re-assignment page is now opening and now we are able to save diary 23rd July 2014 : Waiting to get the details : Requirements has been shared on 22nd July
19 | 13559 | Claim Documents preview screen: | c. Document Preview – 18 July 14 (only view of doc as per template- data element mapping is in progress). We need more discussion for clear understanding of trigger point of document generation. | Doubts shared / Waiting to get the details | c) 18-Jul-14 | 17th July 2014 : Meeting Required We need to know the triggering point of each document generation as currently all forms are generating on new claim registration tab 21st July : * 20 forms has been verified and doubts has been noted out Meeting request has been sent for unknown and unmapped fields in forms 23rd July 2014 : Waiting to get the details for event to be generated: Requirements has been shared on 22nd July
20 | - | Claim Functionality | Complete Claim Functionality - 17 July 14. | Need to discuss | d) 17-Jul-14 | 17th July 2014 : In progress 21st July 2014 : we are able to complete claim and also the list of completed claim is coming under claim payment processing for making payments 23rd July 2014 : Functionality is completed , please confirm if any more we need to add
21 | 13303 | Reserve Tab | UI has been delivered. Processing is in progress and may require further discussion. | Completed |  | 21st July 2014: * Claim reserve tab is working 23rd July 2014: Completed Reserve screen working , Please confirm the working
22 | 13303 | Payment Tab | UI has been delivered. Processing is in progress and may require further discussion. | completed |  | 21st July 2014: * Payment tab Is working We need to finalize payment tab work flow , We Need to know if any gaps are there on page with actual requirement or not 23rd July 2014 : Completed Payment screen working , Please confirm the working
23 |  | Claim Payment Menu: | Claim Payment Processing – flow will be completed by 21 July 14. We need discussion on it. | Under development | 21-Jul-14 | 15th July 2014 : Pending 17th July 2014 : Claim procession discussion meeting required
|  | Claim Payment Menu: | Claim Payment Document Enquiry – need to finalize the UI layout for this menu. |  |  | 23rd July 2014 : For Payment document enquiry : waiting to get the details
24 | 13744 | Claim Recovery Menu: | Need to understand UI and Data elements | Under development |  | 15th July 2014 : Pending 17th July : Meeting required 21st July 2014 : * Meeting request has been sent on 17th July asking for UI information of claim Recovery 23rd July 2014 : Under review , Details has been received on 22nd July 24th July 2014 : under development Mockup screen updated in tfs
25 | 13731 | Enquiry Menu: | Need to understand Requirement | Under development |  | 15th July : Pending 17th July 2014 : Meeting required 21st July 2014 : under process as we got details on 21st July In case of doubts we will call for meeting 23rd July 2014 : Under development
26 |  | In Whole System: | Suggestion: Any fields that require User to input Yes / No to have Radio Button Selection instead of Dropdown | On hold and from now on we can implement radio button |  | 17th July 2014 : Suggestion given 24th July 2014 : Under Review | We are focusing on other issues , In future if client specifically as then we will consider this change request
27 | 13743 : Claim doc enquiry | Enquiry → claim Document printed menu | we need UI and Data element details for this menu | Under development
28 | - | Claim Transaction tab | Is this the part of transaction tab which is coming right now or we need to create Transaction history tab for the screen you provided ? | under discussion |  | 23rd july : dexter has sent requirement 24th july : doubts has been raised
29