## Project status
S.no. | TFS ID | Module | Requirement / Issue Description | Current status | Target Date | Delivery Date | Requirement/Issue Create date | Indian Team Remarks | Singapore Team Remarks | Reference document name
1 | 13670 Parent id is 13302 | Claim screen : Add button Labeled as 'View Reserve History'. | Location of button: New claim registration menu → Claim tab → Initial Reserve frame → Besides Total reserve label. Output : Reserve History button should show , Reserve history against claimant in descending order ( latest to oldest date ) | Completed | 2014-07-17
2 | 13671 Parent id is 13303 |  |  | Completed | 2014-07-16 |  |  | 17-Jul-14: Not Done
3 | 13339, | Text of Labels need to be change | I) Current Transaction Reserve change into “Reserve Movement “ ii) Reserve Movement change into “Current Reserve “ Location: Under Reserve tab | Completed |  |  |  | Done
4 | 13339, | Add one button under “Reserve tab” labeled as “View Reserve History “. | Note: By clicking on this button , Reserve History of all the claimant need to be displayed in date wise in descending order. | Completed |  |  |  | Done
5 | 13672 Parent id : 13339 | Add one button under “Payment tab” labeled as “View Payment History “. | Note : By clicking on this button , Payment History of all claimant need to be displayed in date wise in descending order. | Completed |  |  |  | Done
6 | 13339 | Add options in drop down list: |  | Completed |  |  |  | Done
7 | 13339 | Remove one Drop down list, labeled as 'Category'. | Location: Under Payment tab | Completed |  |  |  | Done
8 | 13339 | Location of Payee need to be replace with removed 'Category' and the text box need to be enlarged . | Location: Under Payment tab | Completed |  |  |  | Done
9 | 13339 | Payment Due date needed to be shifted upward. | Location: Under Payment tab | Completed |  |  |  | Done
10 | 13339, | All labeled text as ' Base' needed to be changed as ' Local '. | Location: Under all tab wherever applicable | Completed |  |  |  | Done
11 | 13673 Parent id is 13303 |  |  | Completed | 2014-07-16 |  |  | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
12 | 13673 Parent id is 13303 |  |  | Completed | 2014-07-16 |  |  | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
13 | 13674 | Claim Adjustments menu : | Requirement to make all tabs non editable except reserve tab | Completed | 2014-07-17
14 | 13675 | In Claim Inquiry Menu: | * Requirement to make all tabs non editable | Completed | 2014-07-17
15 | 13676 | In Claim Payment Menu: | I) Remove Incomplete claims menu completely II) In Claim Payment processing Menu : User can make only payment , other tabs will be for view only, no changes can be made in other tabs information. | Completed | 2014-07-16 |  |  | Done
16 | 13321 | In System Admin Menu: | Complete Office Duty Roster | Completed | 2014-07-16
17 | 12849 | Task Screen | Layout and page elements needed | Waiting to get details |  |  |  | Please provide functionality , UI and Data elements details for this menu | Mr. Yip will check and get back
18 | 13517 | Diary Reassignment | Module functionality | Waiting to get details | b) 18-Jul-14 |  |  |  |  | CDGI - Diary ReAssignment_commented varun 29 july 2014 V2
19 | 13559 | Claim Documents preview screen: | c. Document Preview – 18 July 14 (only view of doc as per template- data element mapping is in progress). We need more discussion for clear understanding of trigger point of document generation. | Waiting to get details | c) 18-Jul-14 |  |  | Doubts shared : I) triggering points of generation ii) condition based form generation Iii) Excel file forms iv)Triggering points for Reports generation 5-August-2014 * Form Format :Already confirmed from Mr. yip for only one format ( PDF ) to be followed. * Please refer attached email copy . * Please give us list of excel reports to be generated from system | There will be only 3 formats: PDF for fully mapped Documents, Word Document for partially mapped Document and CSV For Excel Reports. CDGI will inform us which types after the layout and fields for the system are completed
20 | - | Claim Functionality | Complete Claim Functionality - 17 July 14. | completed | d) 17-Jul-14 |  |  | I) triggering points of generation
21 | 13303 | Reserve Tab | UI has been delivered. Processing is in progress and may require further discussion. | Completed |  |  |  | ii) condition based form generation
22 | 13303 | Payment Tab | UI has been delivered. Processing is in progress and may require further discussion. | completed |  |  |  | Iii) Excel file forms
23 | 13339 | Claim Payment Menu: | Claim Payment Processing – flow will be completed by 21 July 14. We need discussion on it. | completed | 21-Jul-14
|  | Claim Payment Document Enquiry | Need to finalize the UI layout for this menu. | Waiting to get details |  |  |  | Please provide functionality , UI and Data elements details for this menu 5-Aug-2014 : * Please provide information of documents which are related with “ Payment “ | Layout to be the same as Claims Document Printed. The System must filter out those generated Claims Payment Documents
24 | 13744 | Claim Recovery Menu: | Need to understand UI and Data elements | Released and to be reviewed |  | 8 August 2014 | July of 2014 | Please check and confirm working of recovery process menu
25 | 13731 | Enquiry Menu → claims | Need to understand Requirement of UI and data elements | Released and to be reviewed |  | 8 August 2014 | July of 2014 |  |  | 1) claim enquiry screen mail by mr yip 2) Claims Enquiry UI feedback
26 |  | In Whole System: | Suggestion: Any fields that require User to input Yes / No to have Radio Button Selection instead of Dropdown | On hold |  |  | July of 2014 | Ebix india : We are focusing on other issues , In future if client specifically as then we will consider this change request
27 | 13743 : Claim doc enquiry | Enquiry → claim Document printed menu | We need UI and Data element details for this menu | Under development |  |  | July of 2014 |  | 29-july-2014 : search record will display records as per mentioned in doc and view button will display filled document | 1) CDGI - Requirements For Claim Recovery Field 2) Claims Recovery screen feedback
28 |  | Claim Transaction tab | Is this the part of transaction tab which is coming right now or we need to create Transaction history tab for the screen you provided ? | completed
29 | 12910 | User Admin | Email field need to be added in user admin | Under development |  |  | July of 2014
30 | 13517 | Diary Reassignment | Email content needs to be changed which will be sent to re-assigned user | Under development |  |  | July of 2014 |  |  | CDGI - Diary ReAssignment_commented varun 29 july 2014 V2
31 | 13516 | Diary Reassignment | Columns needs to be added in list of diaries : 1) Re-assigned diary? - yes/no 2) Nature of Assignment – temporary/ permanent 3) Re-assignment time frame – “date from” to “date to” | Under development |  |  | July of 2014 |  |  | CDGI - Diary ReAssignment_commented varun 29 july 2014 V2
32 | 13301 | Accident Tab | “ location of Accident “ : field needs to be created on screen | Under development |  |  | July of 2014
33 | 13530 | Notes screen | Raised by Dexter : Notes screen needs to be changed and screen which comes under “ add new note “ can be deleted | On hold |  |  | July of 2014 | We can discuss this in meeting : As Deleting Notes sub screen will disturb layout which is been followed in every screen 5-august-2014 * Please check and confirm existing screen , as it is having functionality of adding notes . * For storing notes record , accident and claim screen needs to be saved first so that claim id can be linked to notes. | Please counter-suggest what is the best layout for user to input notes
33 | 12914 | Home screen header | Deletion Language > Francais | under development |  |  | July of 2014 |  | Done | CDGI Meeting Minutes - 24 July 2014_yip commented.1
34 | 13302,13303,13339 |  | Currency default as SGD Ex rate Default as 1 | under development |  |  | July of 2014 |  |  | CDGI Meeting Minutes - 24 July 2014_yip commented.1
35 | 13339 | Payment and reserve screen | Update Payment and reserve history screen with user name and Date time column | under development |  |  | July of 2014 |  |  | CDGI Meeting Minutes - 24 July 2014_yip commented.1
36 |  | Bus captain listing | To have an Upload Function whereby New Bus Captains can be added. System must not override any existing entries | Waiting to get details |  |  |  | * Please mention screen name on which we need to apply changes * We need to know details of functionality of this requirement to proceed further |  | CDGI Meeting Minutes - 24 July 2014_yip commented.1
37 |  | Document Mapping / Document Generation | To look through the Batch 1 Files and gather the requirements needed for some of the modules, e.g. more fields required for the Third Party Tab | under development |  |  |  |  | 29-Jul-14: CDGI has came back with the Batch 1 of the Document Mapping and some of these Documents highlighted that new fields on some of the modules are required
38 | 13670 Parent id is 13302 | Claim screen | Reserve history button text needs to be changed as “View Reserve & Payment History” | under development | [5 empty] | 1) CDGI - Reserve & Payable To.docx 2) Original document : CDGI Claims Screen comments 3) Reserve history Claim tab CDGI Claims Screen varun_comments_31 july 2014
39 | 13302 | Claim screen | Enhancements to the Claim Amount/Payout Section to allows Users to make multiple payment entries | On hold |  |  |  | * Requirements of Document having functionality of the claim amount / payout section has been raised * Client will confirm for payable to and claim amount / payout working |  | CDGI - Reserve & Payable To.docx
40 | 13302 | Claim Screen | Payable to needs to be changed as simple text field from drop down list | On hold |  |  |  | Client will confirm for payable to and claim amount / payout working |  | CDGI - Reserve & Payable To.docx
41 |  | Diaried Items | Data Elements and user interface details required for sub menu under Diary Listing | Waiting to get details |  |  |  | Please provide functionality , UI and Data elements details for this menu | Mr. Yip will check and get back
42 |  | Assigned Tasks | Data Elements and user interface details required for sub menu under Diary Listing | Waiting to get details |  |  |  | Please provide functionality , UI and Data elements details for this menu | Mr. Yip will check and get back
43 |  | Esclation Tasks | Data Elements and user interface details required for sub menu under Diary Listing | Waiting to get details |  |  |  | Please provide functionality , UI and Data elements details for this menu | Mr. Yip will check and get back
44 |  | Finance Screen | Functionality details of Finance screen : 1) On which menu user can access finance screen 2) Functionality of fields of screen . | Waiting to get details |  |  |  | * we are in process of enabling finance screen on all menus as per informed by dexter
45 | 13301 | Accident Tab | Remove Accident Image Upload Function on Accident Tab and Accident Image Field | under development
46 | 13910 | All system | Implement Sorting System Wide | under development |  |  |  | 1) We need to know fields on which we need to apply sorting functionality : 2) Our understanding : do we need to sort all the drop down list content ? 5-august-2014 Sorting on screen: * Please provide priority screen names to apply sorting to implement before coming Friday and we will implement it on whole system in phases as it is long process. Sorting on drop down list : * It Will be implemented in on going process | 1) Sorting is currently implemented on the Dashboard when the user is logged in. User wants the similar sorting to be implemented for the rest of the layouts, e.g. New Claims Registration's and Claims Payment Search Results 2) We need to sort any drop down list content alphabetically 12-August 2014: Apply Column Sorting on Claims Registration Module - The First Four Screens, if not, New Claims Registration & Incomplete Claims Registration first by Friday
47 |  | Recovery | Recovery sub menu under Claims recovery , we need to know functionality of this module | Waiting to get details |  |  |  | Please provide functionality ,UI and Data elements details for this menu | Will discuss with CDGI this Friday
49 |  | Attachment Tab |  | Question |  |  |  | 5-august-2014 : We need more details to implement this functionality : Some of our queries are listed below: 1) How many folders needs to be created 2) UI details of permission assigning module | CDGI is asking if specified folders can be created for the Attachment Tab and Master Admin can assign rights for these folders 12-August 2014: The current understanding from CDGI is that there will be around 4 folders (maximum) and Super Admin can go to Group Master Details to allow access to any or all of these 4 folders. Follow the layout of the Claims Screen and add a New Section - Attachment and below it are the four folders
50 |  | Reserve Tab | [5 empty] | 5-august-2014 : Please clarify following * “Transaction reserve “ is for current reserve (Final reserve amount ) , do we need to change it to “ outstanding reserve “ or should we change it as “ current reserve “ . | To Change Transaction Reserve Label to Outstanding Reserve (to make it easier for user to understand)
51 |  | View Reserve & History Button to move | [5 empty] | 5-august-2014 : *Claim Adjustment : we are proceeding to add this button * Claim Enquiry : As this module is finalized as per mr. yip mail , we are putting this requirement on hold and attaching Mr. yip mail for reference | To Move the View Reserve & History Button to the Claims Adjustment and Claims Enquiry Screen
52 |  | Master Document Templates |  | Question |  |  |  | * If any template needs to be changed then it needs to be sent to us and then we will modify it , so that user can generated modified template | CDGI is asking if Master Templates can be edited from the backend (e.g. edit one or two paragraphs) before allowing user to generate the document
53 | 13912 | Claim registration module | Search screen changes | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
54 | 13913 | Claim Recovery Menu: | Search screen changes | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
55 | 13914 | Claim Payment Menu: | Search screen changes | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
56 | 13915 | New claim registration | Previous , next two button add , cancel button label change | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
57 | 13916 | Incomplete registration | Previous , next two button add , cancel button label change | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
58 | 13917 | Claim screen | 1) Record creation section : time stamp add 2) Deletion of record section : Change labels 3) Resize of Deletion reason box 4) Claim amount / payout section delete | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
59 | 13339 | Reserve screen | Initial reserve must record in reserve screen | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
60 | 13615 | Depot master | depot master data link with claim screen depot/workshop master field |  |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
61 | 13918 | 3rd party screen | Drop down list “ other party type “ changes | On hold |  |  | 8 august 2014 | Please go through queries mentioned in “ list of requirements – 08 august 2014 “ |  | List Of Requirements - 08 August 2014
62 | 13919 | LOU rate master screen creation | Master screen creation for LOU rate | On hold |  |  | 8 august 2014 | Please go through queries mentioned in “ list of requirements – 08 august 2014 “ |  | List Of Requirements - 08 August 2014
63 | 13920 | Hospital/Clinic master screen creation | Master screen creation for Hospital / clinic master screen | On hold |  |  | 8 august 2014 | Please go through queries mentioned in “ list of requirements – 08 august 2014 “ |  | List Of Requirements - 08 August 2014
64 | 13301 | Accident screen | Is recovery label change as Recoverable Vehicle | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
65 | 13516 | Diary Screen | 1) Remove email column from the screen 2) change “ add new Parties “ with “ add new diary “ | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014
66 |  | Payment and finance screen | Changes To The Payment Tab | On hold |  |  | 8 august 2014 | Please go through queries mentioned in “ list of requirements – 08 august 2014 “ |  | List Of Requirements - 08 August 2014
67 | 13922 Child of 13531 | Transaction screen | Make all fields mandatory | under development |  |  | 8 august 2014 |  |  | List Of Requirements - 08 August 2014

## Description of columns
S.no. | Column names | Column Description | Column status
1 | TFS ID | TFS ID to get all details related with the requirement from TFS software
2 | Module | Module / Screen name by related Requirement/Issue
3 | Requirement / Issue Description | Description of Requirement , will be filled at the time of adding new requirment
4 | Current status | This column gives information of requirement status . Four status can be mentioned : 1. Under development 2. Completed 3. Waiting to get details 4. On hold 1. Under development -> We have got details of requirements and we are in the process of development 2. Completed -> Requirement is deployed on MCAS application and ready to be reviewed by Singapore Team 3. Waiting to get details -> We have shared our doubts and waiting to get feedback so that we can make it Under development. It gives more flexibility as you can also view requirement on which we are waiting to get details from Singapore team. 4. On hold -> This status is for requirement for which India team has got all details but not putting requirement under development . Reasons can be shared in " India team remarks column ". 5) Under Review → Internal team review 6) Released and to be reviewed → Requirement has been resolved and ready to be reviewed by Singapore team. Note : * Current Status can be used for viewing outstanding tasks by filtering out completed value from the filter list and select " Under Development , Waiting to get details , On hold " status from the list of "Filter function ".
5 | Target Date | To be filled by Singapore team , so that we can have a time line to deploy requirements on MCAS . In case of any concern India team will put their comments on "India team remarks" column.
6 | Delivery Date | This Date to be filled by India team as and when Delivery for the requirement happen.
7 | Date wise activity description | If any considerable event happen for the requirement then that can be mapped on this column. For and example : Date of raising any issue , Date of Alteration of requirement. | Deleted
8 | Indian Team Remarks | Remarks from Indian team can be inserted in this column
9 | Singapore Team Remarks | Remarks from Singapore team can be inserted in this column
10 | Reference document name | Name of business requirement document can be mentioned in this column. In case of document gets updated then that updated version name will be updated in this column.
11 | Requirement / Issue create date