## Project status
S.NO. | TFS ID | Module | Requirement / Issue Description | Current status | Target Date | Delivery Date | Date wise activity description | Indian Team Remarks | Singapore Team Remarks | Reference document name
1 | 13670 Parent id is 13302 | Claim screen : Add button Labeled as 'View Reserve History'. | Location of button: New claim registration menu → Claim tab → Initial Reserve frame → Besides Total reserve label. Output : Reserve History button should show , Reserve history against claimant in descending order ( latest to oldest date ) | Completed | 2014-07-17 |  | 15th July 2014 : PENDING 17th July 2014 : Completed
2 | 13671 Parent id is 13303 |  |  | Completed | 2014-07-16 |  | 17th July 2014 : Completed | 17-Jul-14: Not Done
3 | 13339, | Text of Labels need to be change | I) Current Transaction Reserve change into “Reserve Movement “ ii) Reserve Movement change into “Current Reserve “ Location: Under Reserve tab | Completed |  |  | 17th July 2014 : Completed | Done
4 | 13339, | Add one button under “Reserve tab” labeled as “View Reserve History “. | Note: By clicking on this button , Reserve History of all the claimant need to be displayed in date wise in descending order. | Completed |  |  | 17th July 2014 : Completed | Done
5 | 13672 Parent id : 13339 | Add one button under “Payment tab” labeled as “View Payment History “. | Note : By clicking on this button , Payment History of all claimant need to be displayed in date wise in descending order. | Completed |  |  | 17th July 2014 : Completed | Done
6 | 13339 | Add options in drop down list: |  | Completed |  |  | 17th July 2014 : Completed | Done
7 | 13339 | Remove one Drop down list, labeled as 'Category'. | Location: Under Payment tab | Completed |  |  | 17th July 2014 : Completed | Done
8 | 13339 | Location of Payee need to be replace with removed 'Category' and the text box need to be enlarged . | Location: Under Payment tab | Completed |  |  | 17th July 2014 : Completed | Done
9 | 13339 | Payment Due date needed to be shifted upward. | Location: Under Payment tab | Completed |  |  | 17th July 2014 : Completed | Done
10 | 13339, | All labeled text as ' Base' needed to be changed as ' Local '. | Location: Under all tab wherever applicable | Completed |  |  | 17th July 2014 : Completed | Done
11 | 13673 Parent id is 13303 |  |  | Completed | 2014-07-16 |  | 17th July 2014 : Completed | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
12 | 13673 Parent id is 13303 |  |  | Completed | 2014-07-16 |  | 17th July 2014 : Completed | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
13 | 13674 | Claim Adjustments menu : | Requirement to make all tabs non editable except reserve tab | Completed | 2014-07-17 |  | 17th July 2014 : Completed
14 | 13675 | In Claim Inquiry Menu: | * Requirement to make all tabs non editable | Completed | 2014-07-17 |  | 17th July 2014 : Completed
15 | 13676 | In Claim Payment Menu: | I) Remove Incomplete claims menu completely II) In Claim Payment processing Menu : User can make only payment , other tabs will be for view only, no changes can be made in other tabs information. | Completed | 2014-07-16 |  | 17th July 2014 : Completed | Done
16 | 13321 | In System Admin Menu: | Complete Office Duty Roster | Completed | 2014-07-16 |  | 17th July 2014 : Completed
17 | 12849 | Task Screen | Layout and page elements needed | Waiting to get details |  |  | 17th July 2014 : Meeting required to understand Task tab 21st July 2014 : Functionality of Tasks tab Needs to be discussed 23rd July 2014 Waiting to get the details : Requirements has been shared on 22nd July
18 | 13517 | Diary Reassignment | Module functionality | Waiting to get details | b) 18-Jul-14 |  | 17th July 2014 : Meeting Required * Need to discuss and confirm Layout and page elements of diary reassignment which is already created 21st July 2014: Diary re-assignment page is now opening and now we are able to save diary 23rd July 2014 : Waiting to get the details : Requirements has been shared on 22nd July 24th July 2014 : Diary Re-assignment requirements / question has been raised |  |  | CDGI - Diary ReAssignment_commented varun 29 july 2014 V2
19 | 13559 | Claim Documents preview screen: | c. Document Preview – 18 July 14 (only view of doc as per template- data element mapping is in progress). We need more discussion for clear understanding of trigger point of document generation. | Waiting to get details | c) 18-Jul-14 |  | 17th July 2014 : Meeting Required We need to know the triggering point of each document generation as currently all forms are generating on new claim registration tab 21st July : * 20 forms has been verified and doubts has been noted out Meeting request has been sent for unknown and unmapped fields in forms 23rd July 2014 : Waiting to get the details for event to be generated: Requirements has been shared on 22nd July | Doubts shared : I) triggering points of generation ii) condition based form generation Iii) Excel file forms iv)Triggering points for Reports generation
20 | - | Claim Functionality | Complete Claim Functionality - 17 July 14. | completed | d) 17-Jul-14 |  | 17th July 2014 : In progress 21st July 2014 : we are able to complete claim and also the list of completed claim is coming under claim payment processing for making payments 23rd July 2014 : Functionality is completed , please confirm if any more we need to add | I) triggering points of generation
21 | 13303 | Reserve Tab | UI has been delivered. Processing is in progress and may require further discussion. | Completed |  |  | 21st July 2014: * Claim reserve tab is working 23rd July 2014: Completed Reserve screen working , Please confirm the working | ii) condition based form generation
22 | 13303 | Payment Tab | UI has been delivered. Processing is in progress and may require further discussion. | completed |  |  | 21st July 2014: * Payment tab Is working We need to finalize payment tab work flow , We Need to know if any gaps are there on page with actual requirement or not 23rd July 2014 : Completed Payment screen working , Please confirm the working | Iii) Excel file forms
23 | 13339 | Claim Payment Menu: | Claim Payment Processing – flow will be completed by 21 July 14. We need discussion on it. | completed | 21-Jul-14 |  | 15th July 2014 : Pending 17th July 2014 : Claim processing discussion meeting required
|  | Claim Payment Document Enquiry | Need to finalize the UI layout for this menu. | Waiting to get details |  |  | 23rd July 2014 : For Payment document enquiry : waiting to get the details
24 | 13744 | Claim Recovery Menu: | Need to understand UI and Data elements | Under development
25 | 13731 | Enquiry Menu → claims | Need to understand Requirement of UI and data elements | Under development | [5 empty] | 1) claim enquiry screen mail by mr yip 2) Claims Enquiry UI feedback
26 |  | In Whole System: | Suggestion: Any fields that require User to input Yes / No to have Radio Button Selection instead of Dropdown | On hold |  |  | 17th July 2014 : Suggestion given 24th July 2014 : Under Review | Ebix india : We are focusing on other issues , In future if client specifically as then we will consider this change request
27 | 13743 : Claim doc enquiry | Enquiry → claim Document printed menu | We need UI and Data element details for this menu | Under development |  |  |  |  | 29-july-2014 : search record will display records as per mentioned in doc and view button will display filled document | 1) CDGI - Requirements For Claim Recovery Field 2) Claims Recovery screen feedback
28 | 13812 | Claim Transaction tab | Is this the part of transaction tab which is coming right now or we need to create Transaction history tab for the screen you provided ? | Waiting to get details |  |  | 23rd July : Dexter has sent requirement 24th July : doubts has been raised
29 | 12910 | User Admin | Email field need to be added in user admin | Under development |  |  | 22nd July 2014 : approved to be for process and under development
30 | 13517 | Diary Reassignment | Email content needs to be changed which will be sent to re-assigned user | Under development | [5 empty] | CDGI - Diary ReAssignment_commented varun 29 july 2014 V2
31 | 13516 | Diary Reassignment | Columns needs to be added in list of diaries : 1) Re-assigned diary? - yes/no 2) Nature of Assignment – temporary/ permanent 3) Re-assignment time frame – “date from” to “date to” | Under development | [5 empty] | CDGI - Diary ReAssignment_commented varun 29 july 2014 V2
32 | 13301 | Accident Tab | “ location of Accident “ : field needs to be created on screen | Under development |  |  | 22nd July 2014 : Query has been agreed raised
33 | 13530 | Notes screen | Raised by Dexter : Notes screen needs to be changed and screen which comes under “ add new note “ can be deleted | On hold |  |  | 24th July 2014 : Query has been raised | We can discuss this in meeting : As Deleting Notes sub screen will disturb layout which is been followed in every screen
Claim document printed
33 | 12914 | Home screen header | Deletion Language > Francais | under development | [5 empty] | CDGI Meeting Minutes - 24 July 2014_yip commented.1
34 | 13302,13303,13339 |  | Currency default as SGD Ex rate Default as 1 | under development | [5 empty] | CDGI Meeting Minutes - 24 July 2014_yip commented.1
35 | 13339 | Payment and reserve screen | Update Payment and reserve history screen with user name and Date time column | under development | [5 empty] | CDGI Meeting Minutes - 24 July 2014_yip commented.1
36 |  | Bus captain listing |  | Waiting to get details |  |  | 29th july : got requirement and raised doubts |  |  | CDGI Meeting Minutes - 24 July 2014_yip commented.1
37 |  | Document Mapping / Document Generation | To look through the Batch 1 Files and gather the requirements needed for some of the modules, e.g. more fields required for the Third Party Tab | Under review. |  |  |  |  | 29-Jul-14: CDGI has came back with the Batch 1 of the Document Mapping and some of these Documents highlighted that new fields on some of the modules are required
38 | 13670 Parent id is 13302 | Reserve History & Payable To (Under Claims) | Need to change to View Reserve & Payment History as well as make | On hold |  |  |  | View reserve history requirement already mentioned in s.no. 1 of this file and in completed mode . Please do confirm base document so that we can freeze this requirement. |  | 1) CDGI - Reserve & Payable To.docx 2) Original document : CDGI Claims Screen comments 3) Reserve history Claim tab CDGI Claims Screen varun_comments_31 july 2014
39 |  | Claim screen | Enhancements to the Claim Amount/Payout Section to allows Users to make multiple payment entries | On hold |  |  |  | Requirements of Document having functionality of the claim amount / payout section has been raised |  | CDGI - Reserve & Payable To.docx
40 | 13302 | Claim Screen | payable to needs to be changed as simple text field from drop down list | under development | [5 empty] | CDGI - Reserve & Payable To.docx
41 |  |  | Remove Accident Image Upload Function on Accident Tab and Accident Image Field | [6 empty] | `
42 |  |  | Implement Sorting System Wide | [6 empty] | `

## Description of columns
S.no. | Column names | Column Description
1 | TFS ID | TFS ID to get all details related with the requirement from TFS software
2 | Module | Module / Screen name by related Requirement/Issue
3 | Requirement / Issue Description | Description of Requirement , will be filled at the time of adding new requirment
4 | Current status | This column gives information of requirement status . Four status can be mentioned : 1. Under development 2. Completed 3. Waiting to get details 4. On hold 1. Under development -> We have got details of requirements and we are in the process of development 2. Completed -> Requirement is deployed on MCAS application and ready to be reviewed by Singapore Team 3. Waiting to get details -> We have shared our doubts and waiting to get feedback so that we can make it Under development. It gives more flexibility as you can also view requirement on which we are waiting to get details from Singapore team. 4. On hold -> This status is for requirement for which India team has got all details but not putting requirement under development . Reasons can be shared in " India team remarks column ". Note : * Current Status can be used for viewing outstanding tasks by filtering out completed value from the filter list and select " Under Development , Waiting to get details , On hold " status from the list of "Filter function ".
5 | Target Date | To be filled by Singapore team , so that we can have a time line to deploy requirements on MCAS . In case of any concern India team will put their comments on "India team remarks" column.
6 | Delivery Date | This Date to be filled by India team as and when Delivery for the requirement happen.
7 | Date wise activity description | If any considerable event happen for the requirement then that can be mapped on this column. For and example : Date of raising any issue , Date of Alteration of requirement.
8 | Indian Team Remarks | Remarks from Indian team can be inserted in this column
9 | Singapore Team Remarks | Remarks from Singapore team can be inserted in this column
10 | Reference document name | Name of business requirement document can be mentioned in this column. In case of document gets updated then that updated version name will be updated in this column.