## Project status
New Requirements/Changes
Project : MCAS
S.NO. | TFS ID | Module | Requirement / Issue Description | Current status | Target Date | Date wise activity description | Remarks | Reference document
1 | 13670 Parent id is 13302 | Claim screen : Add button Labeled as 'View Reserve History'. | Location of button: New claim registration menu → Claim tab → Initial Reserve frame → Besides Total reserve label. Output : Reserve History button should show , Reserve history against claimant in descending order ( latest to oldest date ) | Completed | 2014-07-17 | 15th July 2014 : PENDING 17th July 2014 : Completed
2 | 13671 Parent id is 13303 | 3rd party screen : Following four options needed to add in Drop down list labeled as 'Payable To'. | i) Claimant ii) Third Party Adjuster iii) Third Party Lawyer iv) Third Party workshop Location: New claim registration menu → 3rd Party tab → claim Amount/ Payout frame → Payable to drop down list. | Completed | 2014-07-16 | 17th July 2014 : Completed | 17-Jul-14: Not Done
3 | 13339, | Text of Labels need to be change | I) Current Transaction Reserve change into “Reserve Movement “ ii) Reserve Movement change into “Current Reserve “ Location: Under Reserve tab | Completed |  | 17th July 2014 : Completed | Done
4 | 13339, | Add one button under “Reserve tab” labeled as “View Reserve History “. | Note: By clicking on this button , Reserve History of all the claimant need to be displayed in date wise in descending order. | Completed |  | 17th July 2014 : Completed | Done
5 | 13672 Parent id : 13339 | Add one button under “Payment tab” labeled as “View Payment History “. | Note : By clicking on this button , Payment History of all claimant need to be displayed in date wise in descending order. | Completed |  | 17th July 2014 : Completed | Done
6 | 13339 | Add options in drop down list: | Drop down list label = 'Payee type' List values: 1) Workshop, 2) Adjuster, 3) Lawyer, 4) Claimant. Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
7 | 13339 | Remove one Drop down list, labeled as 'Category'. | Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
8 | 13339 | Location of Payee need to be replace with removed 'Category' and the text box need to be enlarged . | Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
9 | 13339 | Payment Due date needed to be shifted upward. | Location: Under Payment tab | Completed |  | 17th July 2014 : Completed | Done
10 | 13339, | All labeled text as ' Base' needed to be changed as ' Local '. | Location: Under all tab wherever applicable | Completed |  | 17th July 2014 : Completed | Done
11 | 13673 Parent id is 13303 | Reserve screen : Text boxes size need to be re sized under 3rd party tab , in Initial Reserve frame. | Reserve Ex. Rate Upto digits mentioned Expense Ex. Rate Upto digits mentioned Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Completed | 2014-07-16 | 17th July 2014 : Completed | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
12 | 13673 Parent id is 13303 | Reserve Screen : Text boxes size need to be re sized under 3rd party tab , in 'Claim Amount / Payout' frame. | SGD Upto digits mentioned Claim Amount ` Ex. Rate Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Completed | 2014-07-16 | 17th July 2014 : Completed | 17-Jul-14: Text Boxes are now too small. Need to be able to display till 1,000,000.00 and numbers to have comma separated
13 | 13674 | Claim Adjustments menu : | Requirement to make all tabs non editable except reserve tab | Completed | 2014-07-17 | 17th July 2014 : Completed
14 | 13675 | In Claim Inquiry Menu: | * Requirement to make all tabs non editable | Completed | 2014-07-17 | 17th July 2014 : Completed
15 | 13676 | In Claim Payment Menu: | I) Remove Incomplete claims menu completely II) In Claim Payment processing Menu : User can make only payment , other tabs will be for view only, no changes can be made in other tabs information. | Completed | 2014-07-16 | 17th July 2014 : Completed | Done
16 | 13321 | In System Admin Menu: | Complete Office Duty Roster | Completed | 2014-07-16 | 17th July 2014 : Completed
17 | 12849 | Task Screen | Layout and page elements need to be discussed. | Doubts shared / Waiting to get the details |  | 17th July 2014 : Meeting required to understand Task tab 21st July 2014 : Functionality of Tasks tab Needs to be discussed 23rd July 2014 Waiting to get the details : Requirements has been shared on 22nd July
18 | 13517 | Diary Reassignment | Partly done, may need discussion. Email functionality pending, will be completed by 18 July 14. | Share Doubts on requirement doc on 24th July 2014 / Waiting to get the details | b) 18-Jul-14 | 17th July 2014 : Meeting Required * Need to discuss and confirm Layout and page elements of diary reassignment which is already created 21st July 2014: Diary re-assignment page is now opening and now we are able to save diary 23rd July 2014 : Waiting to get the details : Requirements has been shared on 22nd July 24th July 2014 : Diary Re-assignment requirements / question has been raised
19 | 13559 | Claim Documents preview screen: | c. Document Preview – 18 July 14 (only view of doc as per template- data element mapping is in progress). We need more discussion for clear understanding of trigger point of document generation. | Waiting to get the details Doubts shared I) triggering points of generation ii) condition based form generation Iii) Excel file forms iv)Triggering points for Reports generation | c) 18-Jul-14 | 17th July 2014 : Meeting Required We need to know the triggering point of each document generation as currently all forms are generating on new claim registration tab 21st July : * 20 forms has been verified and doubts has been noted out Meeting request has been sent for unknown and unmapped fields in forms 23rd July 2014 : Waiting to get the details for event to be generated: Requirements has been shared on 22nd July
20 | - | Claim Functionality | Complete Claim Functionality - 17 July 14. | completed | d) 17-Jul-14 | 17th July 2014 : In progress 21st July 2014 : we are able to complete claim and also the list of completed claim is coming under claim payment processing for making payments 23rd July 2014 : Functionality is completed , please confirm if any more we need to add
21 | 13303 | Reserve Tab | UI has been delivered. Processing is in progress and may require further discussion. | Completed |  | 21st July 2014: * Claim reserve tab is working 23rd July 2014: Completed Reserve screen working , Please confirm the working
22 | 13303 | Payment Tab | UI has been delivered. Processing is in progress and may require further discussion. | completed |  | 21st July 2014: * Payment tab Is working We need to finalize payment tab work flow , We Need to know if any gaps are there on page with actual requirement or not 23rd July 2014 : Completed Payment screen working , Please confirm the working
23 |  | Claim Payment Menu: | Claim Payment Processing – flow will be completed by 21 July 14. We need discussion on it. |  | 21-Jul-14 | 15th July 2014 : Pending 17th July 2014 : Claim processing discussion meeting required
|  | Claim Payment Menu → Claim Payment Document Enquiry | Need to finalize the UI layout for this menu. | Waiting to get details from client |  | 23rd July 2014 : For Payment document enquiry : waiting to get the details
24 | 13744 | Claim Recovery Menu: | Need to understand UI and Data elements | Under development |  | 15th July 2014 : Pending 17th July : Meeting required 21st July 2014 : * Meeting request has been sent on 17th July asking for UI information of claim Recovery 23rd July 2014 : Under review , Details has been received on 22nd July 24th July 2014 : under development Mockup screen updated in tfs
25 | 13731 | Enquiry Menu → claims | Need to understand Requirement of UI and data elements | Under development |  | 15th July : Pending 17th July 2014 : Meeting required 21st July 2014 : under process as we got details on 21st July In case of doubts we will call for meeting 23rd July 2014 : Under development
26 |  | In Whole System: | Suggestion: Any fields that require User to input Yes / No to have Radio Button Selection instead of Dropdown | On hold as we are focusing on development of modules |  | 17th July 2014 : Suggestion given 24th July 2014 : Under Review | Ebix india : We are focusing on other issues , In future if client specifically as then we will consider this change request
27 | 13743 : Claim doc enquiry | Enquiry → claim Document printed menu | We need UI and Data element details for this menu | Under development
28 | 13531 | Claim Transaction tab | Is this the part of transaction tab which is coming right now or we need to create Transaction history tab for the screen you provided ? | under discussion |  | 23rd July : Dexter has sent requirement 24th July : doubts has been raised
29
29 | 12910 | User Admin | Email field need to be added in user admin | Query raised and waiting for confirmation |  | 22nd July 2014 : approved to be developed :
30 | 13517 | Diary Reassignment | Email content needs to be changed which will be sent to re-assigned user | under internal review
31 | 13517 | Diary Reassignment | Columns needs to be added in list of diaries : 1) Re-assigned diary? - yes/no 2) Nature of Assignment – temporary/ permanent 3) Re-assignment time frame – “date from” to “date to” | under internal review |  | 22nd July 2014 : query has been agreed raised 25th july 2014
32 | 13301 | Accident Tab | “ location of Accident “ : field needs to be created on screen | under internal review |  | 22nd July 2014 : Query has been agreed raised
33 | 13530 | Notes screen | Raised by Dexter : Notes screen needs to be changed and screen which comes under “ add new note “ can be deleted | under internal review |  | 24th July 2014 : Query has been raised