## Sheet1
S/No | Type | Description | Status | CDGI Remarks | EBIX Remarks
1 | Questions / Requirement / Suggestion | Third Party Individual / Insurer Qn 1. Is There A Requirement To Add Multiple Individuals and Insurers during Claim Registration? If yes, we will need to create “Add New Button” as well as a function to save and display the Created Entries. Qn 2. Do we need to keep track of individual's relationship? E.g. Parents, Siblings, Relatives, Husband and Wife, Infants, Children Requirment: We need to have the list of Mandatory and Optional Fields for both Insurer and Individual to create the Pop-ups Suggestion: We intend to provide these Fields under the Third Party Tab. | Outstanding
2 | Questions | Field Structure For BOI Results Field Qn 1. We understand that this is a populated field from CDGI System. We need to the Field Structure of this Field, e.g. the number of max characters and if it is alphanumeric | Outstanding
3 | Confirmation | Payment & Finance Tab To Be Grayed (Inaccessible) We will grayed out Payment Tab and Finance Tab from the rest of the Modules except for Claims Payment > Claims Payment Processing Module. All payment entries will be made from this Module. | Outstanding
4 | Suggestion | Integrate Finance Tab To Payment Tab We intend to integrate Finance Tab into Payment Tab (which means the Finance Tab will be removed from the rest of the Tabs). System will map the value of the Local Currency Field and display in one of the fields in Finance Tab based on the Payment Type Input and will make sure values are balanced before allowing user to save. | Outstanding
5 | Questions | Transaction Tab to be renamed as Mandate Tab Qn 1. We need to know what are the other fields in this Tab that need to be changed? Qn 2. Do we need to have an Approval Folder in this Tab for users with higher payment / credit note / authory limits to approve the Mandate Entries? Qn 3. We need to know what are the Payment Documents (mapped documents) that need to be generated. | Outstanding
6 | Confirmation | View Reserve & Payment History Field To Be Moved To confirm if the View Reserve & Payment History is to be moved to Claims Adjustment and Claims Enquiry Screen. | Outstanding
7 | Confirmation | Claim Amount / Payout To Be Removed To confirm that the Claim Amount / Payout Section is to be removed | Outstanding
8 | Questions | Maintain Hospital Database Qn 1. Do we need to include a database to maintain Hospital Entries (e.g. for LOG and for Document Mapping?). If yes, please let us know the Optional and Mandatory fields for the Add New Hospital Entry. | Outstanding
9 | Requirement | Documents Mapping Output Format We need to know which are the Document Templates files that can be output as PDF / Word Document / CSV Formats | Outstanding
10 | Requirement | Diary Reassignment Workflow We need to know and understand the Diary Reassignment Workflow | Outstanding
11 | Requirement | Bus Captain & Vehicle Upload File Formats We need to have the Bus Captain and Vehicle Upload Files | Outstanding
12 | Requirement | Payment / Credit Note / Authority Limits We need to understand the above limit requirements so as to design the approval process | Outstanding
13 | Requirement | Claims Adjustment Fields We need to know which are the fields that can be edited under the Claims Adjustment Module | Outstanding
14 | Confirmation | Move View Reserve & Payment History Button To confirm if we are to move the View Reserve & Payment History Button to the Claims Adjustment and Claims Enquiry Module. | Outstanding
15 | Confirmation / Requirement | Move LOU Rate & LOU Days Field to Finance Tab To confirm if LOU Rate Field and LOU Days Field are to be moved to Finance Tab, to which section (or new section) and LOU Rate is a dropdown menu showing 250 and 350. Requirement: We need to know the formula, the output label and display type (e.g. Dollar, Numbers) for LOU Rate and LOU Days | Outstanding
16 | Requirement | Attachments We need to know what are the requirements needed for the OCR / Webservices to pull attachment files from CDGI System | Outstanding
17 | Requirement | Diary Dashboard To let us know what is required to be displayed in the Diary Dashboard when a user logs in | Outstanding
18 | Requirement | Field Structure For BOI Results Field Need to the Field Structure of this Field, e.g. the number of max characters and if it is alphanumeric | Outstanding
19 | Question | Mapped Documents Qn 1. What is the trigger point for each mapped documents? | Outstanding
20 | Question | Maintain Hospital Database Qn 1. Do we need to include a database to maintain Hospital Entries (e.g. for LOG and for Document Mapping?). If yes, please let us know the Optional and Mandatory fields for the Add New Hospital Entry. | Outstanding