## Sheet1
New Requirements/Changes recieved on 23rd june 2014
Project : MCAS
S.NO. | Requirement / Issue | Description | Status ( 15 july 2014 ) | Target Date
1 | Add button Labeled as 'View Reserve History'. | Location of button: New claim registration menu → Claim tab → Initial Reserve frame → Besides Total reserve label. Output : Reserve History button should show , Reserve history against claimant in descending order ( latest to oldest date ) | PENDING | 2014-07-17
2 | Following four options needed to add in Drop down list labeled as 'Payable To'. | i) Claimant ii) Third Party Adjuster iii) Third Party Lawyer iv) Third Party workshop Location: New claim registration menu → 3rd Party tab → claim Amount/ Payout frame → Payable to drop down list. | PENDING | 2014-07-16
3 | Text of Labels need to be change | I) Current Transaction Reserve change into “Reserve Movement “ ii) Reserve Movement change into “Current Reserve “ Location: Under Reserve tab | Completed , please verify
4 | Add one button under “Reserve tab” labeled as “View Reserve History “. | Note: By clicking on this button , Reserve History of all the claimant need to be displayed in date wise in descending order. | Completed
5 | Add one button under “Payment tab” labeled as “View Payment History “. | Note : By clicking on this button , Payment History of all claimant need to be displayed in date wise in descending order. | Completed
6 | Add options in drop down list: | Drop down list label = 'Payee type' List values: 1) Workshop, 2) Adjuster, 3) Lawyer, 4) Claimant. Location: Under Payment tab | Completed
7 | Remove one Drop down list, labeled as 'Category'. | Location: Under Payment tab | completed
8 | Location of Payee need to be replace with removed 'Category' and the text box need to be enlarged . | Location: Under Payment tab | completed
9 | Payment Due date needed to be shifted upward. | Location: Under Payment tab | completed
10 | All labeled text as ' Base' needed to be changed as ' Local '. | Location: Under all tab wherever applicable | completed
11 | Text boxes size need to be re sized under 3rd party tab , in Initial Reserve frame. | Reserve Ex. Rate Upto digits mentioned Expense Ex. Rate Upto digits mentioned Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Pending | 2014-07-16
12 | Text boxes size need to be re sized under 3rd party tab , in 'Claim Amount / Payout' frame. | SGD Upto digits mentioned Claim Amount ` Ex. Rate Note: Size of Ex. Rate will be shorten and the middle box need to be enlarged by the same size. | Pending | 2014-07-16
13 | 13) In Claim Adjustments menu: user can change reserves only and other tabs will be view only. |  | Pending * other tabs can be changed * claimant not coming on reserve tab | 2014-07-17
14 | In Claim Inquiry Menu: All tabs needed to be view only , user cant change in this menu. |  | Pending | 2014-07-17
15 | In Claim Payment Menu: | I) Remove Incomplete claims menu completely II) In Claim Payment processing Menu : User can make only payment , other tabs will be for view only, no changes can be made in other tabs information. | 1) Completed 2)Pending | 2014-07-16