## 9th march
Action Points of Meeting
S.No. | Task | Date of request | Responsible person | Source | Status
1 | Updated project plan file with amendment | 2015-01-27 | Dexter Chan | 27 jan 15 meeting | Done
2 | Send format of test cases | 2015-01-27 | Asai | 27 jan 15 meeting | Done
3 | Database Schema | 2015-01-27 | India Ebix Team | 27 jan 15 meeting | Done
4 | UI design for dashboard permission list screen | 2015-01-27 | Varun | 27 jan 15 meeting | Done
5 | Claim officer duty roaster review | 2015-01-27 | India Ebix Team | 27 jan 15 meeting | Done
6 | Service provider field size discuss with CDGI | 2015-01-27 | Dexter Chan | 27 jan 15 meeting | Done
7 | Dairy Listing Menu | 2015-01-27 | Singapore Ebix Team | 27 jan 15 meeting | On Hold
8 | Upload module details standard requirement document | 2015-01-27 | Dexter Chan | 27 jan 15 meeting | Done
9 | Project plan | 2015-02-04 | India Ebix Team | 4th Feb 15 Meeting | Done
*date filling for UI and Development section
10 | Project plan | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | Done
*date filling for Requirement gathering section
11 | Test Case Review and Testing of all masters of MCAS | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | Done
12 | Claim officer duty roaster requirement review | 2015-02-04 | India Ebix Team | 4th Feb 15 Meeting | Done
13 | User manaul of all system admin module application | 2015-02-04 | Varun | 4th Feb 15 Meeting | Done
14 | File Upload UI | 2015-02-04 | India Ebix Team | 4th Feb 15 Meeting | Done
15 | Car Draft PDF file discussion with CDGI and Analysis on basis of current application | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | on hold
16 | CSV file for Claim | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | Done
17 | SAP upload file modules | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | on hold
18 | Project status and requirement file update | 2015-02-26 | Singapore Ebix Team | Mail on 26th | Done
19 | Bus Captain Listing CSV upload file. | 2015-02-26 | Singapore Ebix Team | Discussion with pravesh during call | pending
20 | Requirement document for Audit trail menu of system admin | 2015-02-27 | Singapore Ebix Team | 27th Feb 15 Meeting | On Hold
21 | Additional Master creation requirement | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
22 | LOG Requirement file | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
23 | File upload updated requirement document | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
24 | I Track updation for on priority all current requirement | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
25 | New System Admin Layout for Daily Use and GI Brokering | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
26 | Linking of Vehicle Class, Make and Model | 2015-03-05 | Asai | 5th march 2015 meeting | pending

## 5th march
Action Points of Meeting
S.No. | Task | Date of request | Responsible person | Source | Status on 5th march 2015
1 | Updated project plan file with amendment | 2015-01-27 | Dexter Chan | 27 jan 15 meeting | Done
2 | Send format of test cases | 2015-01-27 | Asai | 27 jan 15 meeting | Done
3 | Database Schema | 2015-01-27 | India Ebix Team | 27 jan 15 meeting | Done
4 | UI design for dashboard permission list screen | 2015-01-27 | Varun | 27 jan 15 meeting | Done
5 | Claim officer duty roaster review | 2015-01-27 | India Ebix Team | 27 jan 15 meeting | Done
6 | Service provider field size discuss with CDGI | 2015-01-27 | Dexter Chan | 27 jan 15 meeting | Done
7 | Dairy Listing Menu | 2015-01-27 | Singapore Ebix Team | 27 jan 15 meeting | pending
8 | Upload module details standard requirement document | 2015-01-27 | Dexter Chan | 27 jan 15 meeting | Done
9 | Project plan *date filling for UI and Development section | 2015-02-04 | India Ebix Team | 4th Feb 15 Meeting | Done
10 | Project plan *date filling for Requirement gathering section | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | Done
11 | Test Case Review and Testing of all masters of MCAS | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | Done
12 | Claim officer duty roaster requirement review | 2015-02-04 | India Ebix Team | 4th Feb 15 Meeting | Done
13 | User manaul of all system admin module application | 2015-02-04 | Varun | 4th Feb 15 Meeting | Done
14 | File Upload UI | 2015-02-04 | India Ebix Team | 4th Feb 15 Meeting | Done
15 | Car Draft PDF file discussion with CDGI and Analysis on basis of current application | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | on hold
16 | CSV file for Claim | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | Done
17 | SAP upload file modules | 2015-02-04 | Singapore Ebix Team | 4th Feb 15 Meeting | on hold
18 | Project status and requirement file update | 2015-02-26 | Singapore Ebix Team | Mail on 26th | pending
19 | Bus Captain Listing CSV upload file. | 2015-02-26 | Singapore Ebix Team | Discussion with pravesh during call | pending
20 | Requirement document for Audit trail menu of system admin | 2015-02-27 | Singapore Ebix Team | 27th Feb 15 Meeting | pending
21 | Additional Master creation requirement | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
22 | LOG Requirement file | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
23 | File upload updated requirement document | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending
24 | I Track updation for on priority all current requirement | 2015-03-05 | Singapore Ebix Team | 5th march 2015 meeting | pending